## Executive Summary
Section | Description
⚠️ TOP REASONS FOR DELAYS & COST OVERRUNS | Based on Marathon Petroleum pilots and multiple site assessments
1. MISUNDERSTANDING OF DEPENDENCIES | Delays and additional costs
• | Perception that APO and Reporting must be deployed together
• | Actually: HAMR should be working well (HAMR 2.3.0+) BEFORE APO
• | Critical to have hierarchies compatible across ACM/M&R/EAS
2. LICENSE MISCALCULATION | Cost overruns, delays if license insufficient
• | Cannot delete tags without licenses - no reclaim after ordering
• | Too many licenses bought but cannot return excess
• | Example: Anacortes reduced by 35% through cleanup
• | License count during migration unreliable but allows proceed
3. IT-FOCUSED PROJECTS (Quality & Usability Ignored) | No focus on quality or usability
• | Optimal configuration gets insufficient attention
• | Delays in providing functional enhancements
• | Custom solutions not prioritized
4. NO PRE-MIGRATION CLEANUP | Delays and ineffective outcomes
• | Hierarchy cleanup required (may take months)
• | Database cleanup and testing (months of work)
• | Corruptions must be fixed in ACM then re-migrate
• | Difficult to adjust hierarchies later in APO
• | Cannot realize full rationalization benefits without quality data
5. APO MATURITY GAPS | Missing features and functionality gaps
• | Custom solutions required for operational excellence
📊 CRITICAL SUCCESS FACTORS | Critical factors for successful migration
Database Health | ACM/HAMR cleanup, ghost tag removal, corruption fixes
License Sizing | Evaluate actual current usage before ordering (30-40% ghost tags common)
Hierarchy Alignment | Ensure ACM/M&R/EAS hierarchies aligned before migration
Custom Solutions | Plan for ACM→APO feature gaps, implement enhanced sync and tools
Training & Change Management | Focus on "what was lost" not just new features
Post-Migration Support | Daily health checks, backup/recovery, continuous improvement

## 0-Pre-Assessment
# | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Assessment Tasks
2 | .1 ACM Database Quality Audit
|  | Assessment checklist: | Site | ☐ Not Started
|  | Invalid tags (tags not in DCS) | Site | ☐ Not Started
|  | Ghost tags (historical tags no longer active) | Site | ☐ Not Started
|  | Tags in wrong assets (hierarchy misalignment) | Site | ☐ Not Started
|  | Corrupted parameters (invalid alarm limits, units, priorities) | Site | ☐ Not Started
|  | SCADA tags requiring cleanup | Site | ☐ Not Started
|  | Duplicate tags and naming inconsistencies | Site | ☐ Not Started
|  | Corrupted notes | Site | ☐ Not Started
|  | Tag description accuracy and completeness | Site | ☐ Not Started
|  | Alarm Help configuration dependencies | Site | ☐ Not Started
|  | Active enforcement mappings | Site | ☐ Not Started
|  | Dynamic mode enforcement configurations | Site | ☐ Not Started
|  | Health check methodology | Site | ☐ Not Started
|  | Tools and queries for assessment | Site | ☐ Not Started
|  | Validate ACM Consoles can map APO Consoles to HAMR Operating Positions | Site | ☐ Not Started
|  | Scoring system: Green/Yellow/Red health status | Site | ☐ Not Started
3 | .2 M&R (Metrics & Reporting) Database Assessment
|  | License consumption analysis: | Site | ☐ Not Started
|  | Identifying ghost tags (no events in M&R) | Site | ☐ Not Started
|  | Tag merging opportunities (e.g., History Index 200, 201, 202...) | Site | ☐ Not Started
|  | Case study: 10,000+ tag spike from invalid Redirection Index tags | Site | ☐ Not Started
|  | Old/corrupted assets removal | Site | ☐ Not Started
|  | Path re-arrangements and optimization | Site | ☐ Not Started
|  | Adjustments of Operating Positions for APO\ACM Console mapping | Site | ☐ Not Started
|  | Unassigned process assets should be addressed | Site | ☐ Not Started
|  | Performance improvement opportunities: | Site | ☐ Not Started
|  | Closing invalid alarms in database | Site | ☐ Not Started
|  | Removing invalid suppressed states | Site | ☐ Not Started
|  | Merging tag descriptions | Site | ☐ Not Started
|  | Retention period review and adjustment | Site | ☐ Not Started
4 | .3 EMDB Integrity Verification
|  | EAS EMDB quality assessment | Site | ☐ Not Started
|  | Automatic comparison tools (identifying discrepancies) | Site | ☐ Not Started
|  | Common EMDB issues discovered: | Site | ☐ Not Started
|  | Inconsistent naming conventions | Site | ☐ Not Started
|  | Orphaned assets | Site | ☐ Not Started
|  | Incorrect hierarchies | Site | ☐ Not Started
|  | Duplicate paths | Site | ☐ Not Started
|  | Cleanup and consolidation procedures | Site | ☐ Not Started
5 | .1 Tag-Level Issues
|  | Non-alarmable tags: Tags that don't meet alarm definition (ISA 18.2) | Site | ☐ Not Started
|  | Invalid tag structures: Tags that will fail migration validation | Site | ☐ Not Started
|  | Tags not in DCS: Historical or test tags still in database | Site | ☐ Not Started
|  | Tag description quality: Incomplete, inaccurate, or missing descriptions | Site | ☐ Not Started
|  | Duplicate tags: Same physical point represented multiple times | Site | ☐ Not Started
|  | Tags in wrong assets: Misaligned with plant hierarchy | Site | ☐ Not Started
|  | BMA tags: Need to be removed prior migration, may need to mitigate with APO 3.1 | Site | ☐ Not Started
|  | Critical question: Will Honeywell provide a process? Or each customer needs to reinvent it? | Site | ☐ Not Started
6 | .2 Parameter-Level Issues
|  | Corrupted parameters: Invalid alarm limits, deadbands, delays | Site | ☐ Not Started
|  | Unit mismatches: Engineering units inconsistent between ACM and DCS | Site | ☐ Not Started
|  | Priority misalignment: Priorities not following rationalization rules | Site | ☐ Not Started
|  | Invalid time parameters: Response times and delay settings | Site | ☐ Not Started
|  | SCADA-specific corruptions: Common in SCADA tag integrations | Site | ☐ Not Started
|  | Notes corruption: May lose alarm help on re-import or notes look unprofessional | Site | ☐ Not Started
7 | .1 M&R Database Assessment
|  | Asset alignment: Ensuring ACM, M&R, and EAS EMDB consistency | Site | ☐ Not Started
|  | Path structure optimization | Site | ☐ Not Started
|  | New paths and reorganization opportunities | Site | ☐ Not Started
|  | Asset migration planning | Site | ☐ Not Started
|  | Addressing unassigned assets or incorrect assets assignments | Site | ☐ Not Started
8 | .1 True License Requirement Calculation
|  | Ghost tag identification and removal | Site | ☐ Not Started
|  | Invalid tag removal | Site | ☐ Not Started
|  | Merging consolidated tags | Site | ☐ Not Started
|  | License consumption projections | Site | ☐ Not Started
|  | Cost impact analysis | Site | ☐ Not Started
9 | .2 License Ordering Strategy
|  | CRITICAL: Cannot reclaim licenses after ordering | Site | ☐ Not Started
|  | Validation procedures before license order | Site | ☐ Not Started
|  | Contingency buffer (recommended: 5-10%) | Site | ☐ Not Started
|  | License type selection (permanent vs. term) | Site | ☐ Not Started
10 | .1 Alarm Help Configuration
|  | Alarm Help Router connections | Site | ☐ Not Started
|  | Alarm Help content dependencies | Site | ☐ Not Started
|  | Custom Alarm Help integrations | Site | ☐ Not Started
|  | Migration impact on Alarm Help availability | Site | ☐ Not Started
11 | .2 Enforcement Dependencies
|  | Static enforcement mappings | Site | ☐ Not Started
|  | Dynamic mode enforcements (highest risk) | Site | ☐ Not Started
|  | Console-specific enforcements | Site | ☐ Not Started
|  | "Reverse enforcement" scenarios (DCS is master) | Site | ☐ Not Started
|  | Example: Dead Band Units controlled only on DCS | Site | ☐ Not Started
|  | Custom enforcement rules requiring special handling | Site | ☐ Not Started
12 | .3 Reporting and Integration Dependencies
|  | M&R reporting schedules and dependencies | Site | ☐ Not Started
|  | Custom reports and dashboards | Site | ☐ Not Started
|  | Third-party system integrations | Site | ☐ Not Started
|  | Data exports and interfaces | Site | ☐ Not Started
13 | .1 Establishing Temporary ACM Environment
|  | Installing temporary Manager Server | Site | ☐ Not Started
|  | Installing temporary Enforcer Server (can be on client/station) | Site | ☐ Not Started
|  | Purpose: Allow cleanup without affecting production operations | Site | ☐ Not Started
|  | Maintaining Alarm Help and enforcement availability | Site | ☐ Not Started
14 | .2 Step-by-Step ACM Cleanup
|  | Corrupted notes | Site | ☐ Not Started
|  | Invalid parameters | Site | ☐ Not Started
15 | .3 M&R Database Optimization
|  | Hierarchy optimization | Site | ☐ Not Started
|  | Ghost tag removal procedures | Site | ☐ Not Started
|  | Asset cleanup and consolidation | Site | ☐ Not Started
|  | Performance optimization (closing invalid alarms, etc.) | Site | ☐ Not Started
|  | Retention adjustment implementation | Site | ☐ Not Started
16 | .4 Validation and Quality Assurance
|  | Pre-cleanup baseline metrics | Site | ☐ Not Started
|  | Post-cleanup validation | Site | ☐ Not Started
|  | Test enforcements and alarm help | Site | ☐ Not Started
|  | Reporting validation | Site | ☐ Not Started
|  | Sign-off criteria for migration readiness | Site | ☐ Not Started

## 0-Cleanup
# | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Cleanup Tasks
ACM Cleanup
|  | Remove ghost tags and orphaned entries | Site | ☐ Not Started
|  | Fix hierarchy corruptions | Site | ☐ Not Started
HAMR Cleanup
|  | Install HAMR 2.3.0+ before APO | Vendor | ☐ Not Started
|  | Remove ghost tags from HAMR database | Site | ☐ Not Started

## 1-Custom Solutions
# | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Custom Solution Tasks
Gap Analysis
|  | Identify ACM→APO feature gaps | Site | ☐ Not Started
Custom Tools
|  | Develop tag export/import tools | Custom | ☐ Not Started
Health Checks
|  | Implement daily health check scripts | Custom | ☐ Not Started

## 2-Pre-Planning
# | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Installation Planning Tasks
2 | .1 Infrastructure Requirements
|  | Server specifications (APO Site Server, Transfer Service) | IT/OT | ☐ Not Started
|  | Network requirements (connectivity to DCS, database servers) | IT/OT | ☐ Not Started
|  | Storage requirements and growth planning | Site | ☐ Not Started
|  | Virtualization considerations | Site | ☐ Not Started
3 | .2 SQL Server Configuration
|  | SQL Server version requirements (compatibility matrix) | IT/OT | ☐ Not Started
|  | Database sizing and performance tuning | Site | ☐ Not Started
|  | SQL permissions and service accounts | IT/OT | ☐ Not Started
|  | SQL Server properties | IT/OT | ☐ Not Started
|  | Transaction log management | Site | ☐ Not Started
|  | Backup infrastructure | IT/OT | ☐ Not Started
4 | .3 Organizational Standards
|  | Schema naming conventions (consistency across sites) | Site | ☐ Not Started
|  | Folder structures and file organization | Site | ☐ Not Started
|  | Service account naming and management | Site | ☐ Not Started
|  | Security group assignments | Site | ☐ Not Started
|  | Documentation standards | Site | ☐ Not Started
5 | .4 Network and Security
|  | Firewall rules and port requirements | Site | ☐ Not Started
|  | Certificate management (SSL/TLS) | Site | ☐ Not Started
|  | Domain trust relationships | Site | ☐ Not Started
|  | OT security compliance | Site | ☐ Not Started
6 | .1 Following Organizational Standards During Install
|  | Standard installation checklists | Site | ☐ Not Started
|  | Standard naming conventions | Site | ☐ Not Started
|  | Standard configurations | Site | ☐ Not Started
|  | Configuration management approach | Site | ☐ Not Started
|  | As-built documentation requirements | Site | ☐ Not Started
7 | .2 Database Creation and Migration
|  | APO database creation procedures | Site | ☐ Not Started
|  | ACM to APO data migration process | Site | ☐ Not Started
|  | Validation of migrated data | Site | ☐ Not Started
8 | .3 Asset Migration Approach
|  | EMDB to APO asset structure mapping | Site | ☐ Not Started
|  | Hierarchy recreation and validation | Site | ☐ Not Started
|  | Console assignment | Site | ☐ Not Started
9 | .4 System Configuration
|  | Site settings and preferences | Site | ☐ Not Started
|  | User authentication (Active Directory integration) | Site | ☐ Not Started
|  | Role-based access control (RBAC) setup | Site | ☐ Not Started
|  | Notification configuration (email alerts, etc.) | Site | ☐ Not Started

## 3-OSW Completion
# | Item # | Task | Owner | Status | Notes | Prerequisites
OSW Data Entry
Assets
|  | Complete Asset Hierarchy (Site→Area→Unit→System→Subsystem) | Site | ☐ Not Started
|  | Validate hierarchy matches FDS standards | Site | ☐ Not Started
Devices
|  | Complete Device Inventory (manufacturer, model, protocol) | Site | ☐ Not Started
|  | Classify external reference devices | Site | ☐ Not Started
|  | Document unsupported devices with justification | Site | ☐ Not Started
External Reference Configuration
ControlLogix
|  | Provide .L5X/.L5K export and I/O config | Site | ☐ Not Started
PLC5/SLC
|  | Provide .RSS export and addressing scheme | Site | ☐ Not Started
Triconex
|  | Confirm EPKS External Reference or TPS import | Site | ☐ Not Started
Bently Nevada
|  | Confirm DCS External Reference method | Site | ☐ Not Started
Analyzers
|  | Decide manual entry vs automated import | Site | ☐ Not Started
OSW Validation
Review
|  | Vendor reviews OSW for completeness | Vendor | ☐ Not Started
|  | Site confirms all devices in scope | Site | ☐ Not Started
|  | ⚠️ NO additions after sign-off without Change Order | Site | ☐ Not Started
Sign-Off
|  | Executive sponsor signs off (scope locked) | Site | ☐ Not Started

## 4-Deployment Readiness
# | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Readiness Tasks
2 | .1 APO R3.0.0 Migration Utility Usage
|  | Migration utility features and capabilities | Site | ☐ Not Started
|  | Pre-migration validation checks | Site | ☐ Not Started
|  | Migration utility configuration | Site | ☐ Not Started
|  | Execution and monitoring | Site | ☐ Not Started
3 | .2 Three-Phase Migration Approach
|  | Phase 1: Pre-migration | Site | ☐ Not Started
|  | Configure essential components | Site | ☐ Not Started
|  | Secure site environment | Site | ☐ Not Started
|  | Validate prerequisites | Site | ☐ Not Started
|  | Validate quality of data | Site | ☐ Not Started
|  | Phase 2: Migration | Site | ☐ Not Started
|  | Validate source data | Site | ☐ Not Started
|  | Map assets and tags | Site | ☐ Not Started
|  | Execute migration utility | Site | ☐ Not Started
|  | Monitor progress | Site | ☐ Not Started
|  | Phase 3: Post-migration | Site | ☐ Not Started
|  | Conduct data integrity reviews | Site | ☐ Not Started
|  | Validation tools execution | Site | ☐ Not Started
|  | Reconciliation reports | Site | ☐ Not Started
|  | Validate quality of data | Site | ☐ Not Started
4 | .3 Data Transformation and Mapping
|  | Tag attribute mapping (ACM to APO) | Site | ☐ Not Started
|  | Priority translation | Site | ☐ Not Started
|  | Alarm type conversions | Site | ☐ Not Started
|  | Custom field mapping | Site | ☐ Not Started
5 | .4 Error Handling and Resolution
|  | Common migration errors and causes | Site | ☐ Not Started
|  | Error log analysis | Site | ☐ Not Started
|  | Remediation procedures | Site | ☐ Not Started
|  | When to restart vs. fix-forward | Site | ☐ Not Started
6 | .5 Data Integrity Verification
|  | Tag count reconciliation | Site | ☐ Not Started
|  | Asset structure validation | Site | ☐ Not Started
|  | Alarm limit verification | Site | ☐ Not Started
|  | Enforcement mapping confirmation | Site | ☐ Not Started
|  | Sample testing approach | Site | ☐ Not Started
7 | .1 Running ACM and APO Concurrently
|  | Infrastructure for parallel operations | Site | ☐ Not Started
|  | Data synchronization strategy | Site | ☐ Not Started
|  | Avoid OPC overload \ overlapping tasks (enforcements, tagsync) | Site | ☐ Not Started
|  | Operator interface management (which system is primary?) | Site | ☐ Not Started
8 | .2 Critical Considerations for Enforcements
|  | Static enforcements: Parallel operation approach | Site | ☐ Not Started
|  | Dynamic mode enforcements: High-risk scenarios | Site | ☐ Not Started
|  | Testing enforcements without impacting DCS | Site | ☐ Not Started
|  | Enforcement cutover planning | Site | ☐ Not Started
9 | .3 Conflict Resolution Procedures
|  | Change request management during parallel operations | Site | ☐ Not Started
|  | Which system is source of truth? | Site | ☐ Not Started
|  | Merging changes from both systems | Site | ☐ Not Started
10 | .4 Performance Monitoring
|  | System resource utilization | Site | ☐ Not Started
|  | Response time monitoring | Site | ☐ Not Started
|  | Operator workload assessment | Site | ☐ Not Started

## 5-Migration Execute
# | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Migration Execution Tasks
Execution
|  | Run ACM to APO migration tool | Vendor | ☐ Not Started
|  | Validate data transfer completeness | Vendor | ☐ Not Started
Configuration
|  | Configure APO site settings | Site | ☐ Not Started

## 6-Validation & Go-Live
# | Item # | Task | Owner | Status | Notes | Prerequisites
Parallel Operation Setup
Configuration
|  | Run ACM and APO in parallel (30-90 days) | Site | ☐ Not Started
|  | Maintain ACM for fallback capability | Site | ☐ Not Started
|  | Monitor both systems for discrepancies | Site | ☐ Not Started
Data Validation
Testing
|  | Compare ACM and APO alarm counts | Site | ☐ Not Started
|  | Validate enforcement execution | Site | ☐ Not Started
|  | Verify reporting accuracy | Site | ☐ Not Started
|  | Test custom solutions in APO | Custom | ☐ Not Started
Performance Validation
Metrics
|  | Monitor sync accuracy (Standard vs Alternative) | Site | ☐ Not Started
|  | Verify KPI calculations match ISA 18.2 requirements | Site | ☐ Not Started
|  | Validate daily health check notifications | Custom | ☐ Not Started

## 7-Cutover
# | Item # | Task | Owner | Status | Notes | Prerequisites
Pre-Cutover
Validation
|  | Final ACM vs APO comparison | Site | ☐ Not Started
|  | ⚠️ CRITICAL: Confirm all enforcements tested | Site | ☐ Not Started
|  | Document any known issues and workarounds | Site | ☐ Not Started
Communication
|  | Notify operations of cutover schedule | Site | ☐ Not Started
Cutover Execution
Cutover
|  | Disable ACM enforcements | Site | ☐ Not Started
|  | Enable APO enforcements | Site | ☐ Not Started
|  | Monitor first 24 hours closely | Site | ☐ Not Started
|  | Verify DCS and APO in sync | Site | ☐ Not Started
ACM Decommission
Decommission
|  | Retain ACM for 90 days as backup | Site | ☐ Not Started
|  | Archive ACM database | Site | ☐ Not Started
|  | Remove ACM services (after approval) | IT/OT | ☐ Not Started

## 8-Post-Migration
# | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Optimization Tasks
2 | .1 Regular Database Maintenance
|  | Weekly maintenance tasks | Site | ☐ Not Started
|  | Monthly optimization activities | Site | ☐ Not Started
|  | Quarterly health assessments | Site | ☐ Not Started
3 | .2 License Optimization (Ongoing)
|  | Ghost tag monitoring and removal | Site | ☐ Not Started
|  | License consumption trending | Site | ☐ Not Started
|  | Optimization opportunities identification | Site | ☐ Not Started
4 | .3 Performance Tuning
|  | Query optimization | Site | ☐ Not Started
|  | Index maintenance | Site | ☐ Not Started
|  | Resource utilization monitoring | Site | ☐ Not Started
5 | .4 User Feedback Incorporation
|  | Regular operator surveys | Site | ☐ Not Started
|  | Usability improvement initiatives | Site | ☐ Not Started
|  | Feature request tracking | Site | ☐ Not Started