## Summary
PC VALUE TRACKER — QUARTERLY SUMMARY
Quarter: | Q4 2025
Generated: | 2026-01-24 17:36
TOTAL ISSUES | 24
BY MONTH | Count
October 2025 | 4
November 2025 | 1
December 2025 | 19
BY STREAM | Count
Day-to-Day | 8 (33.3%)
Unit Support | 4 (16.7%)
Alarm Rationalization | 4 (16.7%)
L1 Integrity, Legacy Modernization | 1 (4.2%)
Legacy Modernization | 1 (4.2%)
Diagnostic | 1 (4.2%)
Alarm Rationalization, Unit Support | 1 (4.2%)
L1 Integrity, Alarm Rationalization, Unit Support | 1 (4.2%)
L1 Integrity, Alarm Rationalization, Legacy Modernization | 1 (4.2%)
L1 Integrity | 1 (4.2%)
L1 Integrity, Alarm Rationalization | 1 (4.2%)
BY SYSTEM | Count
DCS | 7 (29.2%)
Alarm | 7 (29.2%)
Other | 5 (20.8%)
SIS | 3 (12.5%)
PLC | 2 (8.3%)
BY COMPLEXITY | Count
Quick | 1 (4.2%)
Low | 15 (62.5%)
Moderate | 2 (8.3%)
Medium | 2 (8.3%)
Major | 1 (4.2%)
High | 3 (12.5%)
BY BUSINESS IMPACT | Count
Production | 4 (16.7%)
Safety | 13 (54.2%)
Compliance | 1 (4.2%)
Efficiency | 2 (8.3%)
Low | 4 (16.7%)

## Trends
QUARTERLY TRENDS
Month | Total Issues | High Complexity | Top Stream | Top System
Oct 2025 | 4 | 1 | Unit Support | Other
Nov 2025 | 1 | 0 | Day-to-Day | PLC
Dec 2025 | 19 | 5 | Day-to-Day | Alarm

## Stream Scorecard
STREAM SCORECARD
Stream | Count | High Complexity | Safety Impact | Key Systems
Alarm Rationalization | 4 | 1 | 4 | Alarm Mgmt
Alarm Rationalization, Unit Support | 1 | 0 | 1 | Alarm Mgmt
Day-to-Day | 8 | 1 | 3 | Experion/TPS, Historian, Siemens PLC
Diagnostic | 1 | 1 | 1 | ACM/SCADA
L1 Integrity | 1 | 0 | 0 | Experion/TPS
L1 Integrity, Alarm Rationalization | 1 | 0 | 0 | SIS/Triconex
L1 Integrity, Alarm Rationalization, Legacy Modernization | 1 | 1 | 1 | SIS/Triconex
L1 Integrity, Alarm Rationalization, Unit Support | 1 | 0 | 0 | Experion/TPS
L1 Integrity, Legacy Modernization | 1 | 1 | 0 | Experion/TPS
Legacy Modernization | 1 | 0 | 0 | Experion/TPS
Unit Support | 4 | 1 | 3 | SIS/Triconex, GE/Woodward/Bently, PLC (Rockwell)
Date | System | Summary | Complexity | Impact
2025-12-11 | Alarm Mgmt | RE: APO 3.0 Installation: Raised L3/L4 edit constraints and CAR/PAR impacts; pro | Low | Safety
2025-12-11 | Alarm Mgmt | RE: Console / Dynamo: Explained suppression exposure vs. NTE reporting; reviewed | Low | Safety
2025-12-29 | Alarm Mgmt | RE: ACM Secondary Parameter Update: Ran secondary parameter update to push QB de | Low | Safety
2025-12-29 | Alarm Mgmt | RE: ALERT: ACM DB Replication Heartbeat not implemented or cannot be detected: C | High | Safety
Date | System | Summary | Complexity | Impact
2025-12-16 | Alarm Mgmt | SPW Dynamo Activities: Investigated bulk UnSuppress actions and audit behavior a | Low | Safety
Date | System | Summary | Complexity | Impact
2025-10-07 | Historian | RE: Marathon ¦ St Paul ¦ Pre-Onsite Visit: Clarified PI vs. PHD architecture and | Low | Production
2025-11-14 | Siemens PLC |  | Moderate | Production
2025-12-02 | UPS/COM Alarm |  | Moderate | Safety
2025-12-04 | APO/HAM |  | Quick | Efficiency
2025-12-11 | Alarm Mgmt | RE: ETD_UTIL: Provided Tag Sync add/delete lists and reasoning for In-Progress v | Low | Production
2025-12-11 | Experion/TPS | RE: Significant issue with alarm discrepancies occurring between the servers and | Medium | Safety
2025-12-29 | Integrity (ALI) | RE: Zip files transferred correctly as well: Verified transfer job execution fro | Low | Low
2025-12-31 | Experion/TPS | RE: DAS 91DAS005: Chased missing SUPP events on DAS triggers; captured re-init a | Low | Safety
Date | System | Summary | Complexity | Impact
2025-12-14 | ACM/SCADA |  | Major | Safety
Date | System | Summary | Complexity | Impact
2025-12-29 | Experion/TPS | RE: UDC Agents: Tracked redeploys across ESV/EVT fleet; highlighted remaining pr | Low | Low
Date | System | Summary | Complexity | Impact
2025-12-31 | SIS/Triconex | RE: Trident DI Issues - LOV: Pointed to CyberIntegrity inventory capability; not | Low | Production
Date | System | Summary | Complexity | Impact
2025-12-29 | SIS/Triconex | RE: Integrity TS1131 cannot view XPS: Pursued PDF-based workaround and asked for | High | Safety
Date | System | Summary | Complexity | Impact
2025-12-17 | Experion/TPS | RE: LCN3 (ALKY) DCS Backup and Integrity Update: Coordinated D3K EC schedules an | Low | Efficiency
Date | System | Summary | Complexity | Impact
2025-10-21 | Experion/TPS | FW: LARINT01 - Cannot create scheduled task: Documented export cadences (EXP/TPS | High | Low
Date | System | Summary | Complexity | Impact
2025-12-08 | Experion/TPS | FW: Re: DSPPrime on TDC consoles: Shared dspprime/pntbld procedure to purge stal | Low | Low
Date | System | Summary | Complexity | Impact
2025-10-09 | SIS/Triconex | RE: HCU TMR Alarm: Referenced prior EDM training for pulling system faults; reco | Low | Safety
2025-10-23 | GE/Woodward/Bently | WCC 92 Power Distribution Card Failure: Initiated follow-up on power distributio | Low | Compliance
2025-12-11 | PLC (Rockwell) | FW: FCC System Alarm 11SPLC30AO: Analyzed polling performance vs. register gaps; | Low | Safety
2025-12-19 | Experion/TPS | RE: LCN4 17XA861 and 84UA822 chattering alarms: Clarified INHIBIT vs DISABLE par | Medium | Safety

## All Issues
Date | System | Summary | Stream | Complexity | Resolution | Business Impact
2025-10-07 | Historian | RE: Marathon ¦ St Paul ¦ Pre-Onsite Visit: Clarified PI vs. PHD architecture and suggested staging PI utilities post scope approval. | Day-to-Day | Low |  | Production
2025-10-09 | SIS/Triconex | RE: HCU TMR Alarm: Referenced prior EDM training for pulling system faults; recommended shadowing for live troubleshooting. | Unit Support | Low |  | Safety
2025-10-21 | Experion/TPS | FW: LARINT01 - Cannot create scheduled task: Documented export cadences (EXP/TPS) and reiterated scheduled task/batch needs for INT01. | L1 Integrity, Legacy Modernization | High |  | Low
2025-10-23 | GE/Woodward/Bently | WCC 92 Power Distribution Card Failure: Initiated follow-up on power distribution card incident; noted spare strategy considerations. | Unit Support | Low |  | Compliance
2025-11-14 | Siemens PLC |  | Day-to-Day | Moderate |  | Production
2025-12-02 | UPS/COM Alarm |  | Day-to-Day | Moderate |  | Safety
2025-12-04 | APO/HAM |  | Day-to-Day | Quick |  | Efficiency
2025-12-08 | Experion/TPS | FW: Re: DSPPrime on TDC consoles: Shared dspprime/pntbld procedure to purge stale TDC points after cutover. | Legacy Modernization | Low |  | Low
2025-12-11 | PLC (Rockwell) | FW: FCC System Alarm 11SPLC30AO: Analyzed polling performance vs. register gaps; requested change chronology around 12/3. | Unit Support | Low |  | Safety
2025-12-11 | Alarm Mgmt | RE: APO 3.0 Installation: Raised L3/L4 edit constraints and CAR/PAR impacts; proposed template app/db servers and node rename procedure. | Alarm Rationalization | Low |  | Safety
2025-12-11 | Alarm Mgmt | RE: Console / Dynamo: Explained suppression exposure vs. NTE reporting; reviewed specific NTE/level instruments. | Alarm Rationalization | Low |  | Safety
2025-12-11 | Alarm Mgmt | RE: ETD_UTIL: Provided Tag Sync add/delete lists and reasoning for In-Progress versions created by scheduled jobs. | Day-to-Day | Low |  | Production
2025-12-11 | Experion/TPS | RE: Significant issue with alarm discrepancies occurring between the servers and the consoles: Questioned BRM station role; supported EST rebuild plan and MOC path. | Day-to-Day | Medium |  | Safety
2025-12-14 | ACM/SCADA |  | Diagnostic | Major |  | Safety
2025-12-16 | Alarm Mgmt | SPW Dynamo Activities: Investigated bulk UnSuppress actions and audit behavior across TPS/Experion. | Alarm Rationalization, Unit Support | Low |  | Safety
2025-12-17 | Experion/TPS | RE: LCN3 (ALKY) DCS Backup and Integrity Update: Coordinated D3K EC schedules and executed backups for Carson LCNs; requested enabling ECs on ENG stations. | L1 Integrity, Alarm Rationalization, Unit Support | Low |  | Efficiency
2025-12-19 | Experion/TPS | RE: LCN4 17XA861 and 84UA822 chattering alarms: Clarified INHIBIT vs DISABLE parity for suppression reporting; tied to journaling load relief. | Unit Support | Medium |  | Safety
2025-12-29 | SIS/Triconex | RE: Integrity TS1131 cannot view XPS: Pursued PDF-based workaround and asked for model changes (Aha!) to move away from XPS. | L1 Integrity, Alarm Rationalization, Legacy Modernization | High |  | Safety
2025-12-29 | Alarm Mgmt | RE: ACM Secondary Parameter Update: Ran secondary parameter update to push QB description/alarm edits; reported per-tag outcomes. | Alarm Rationalization | Low |  | Safety
2025-12-29 | Alarm Mgmt | RE: ALERT: ACM DB Replication Heartbeat not implemented or cannot be detected: Confirmed the replication/heartbeat condition self-recovered the following day. | Alarm Rationalization | High |  | Safety
2025-12-29 | Integrity (ALI) | RE: Zip files transferred correctly as well: Verified transfer job execution from doublehop to INT01; set expectation on 8+ hour population. | Day-to-Day | Low |  | Low
2025-12-29 | Experion/TPS | RE: UDC Agents: Tracked redeploys across ESV/EVT fleet; highlighted remaining problematic nodes for follow-up. | L1 Integrity | Low |  | Low
2025-12-31 | Experion/TPS | RE: DAS 91DAS005: Chased missing SUPP events on DAS triggers; captured re-init actions; warned about server-wide alarm toggling. | Day-to-Day | Low |  | Safety
2025-12-31 | SIS/Triconex | RE: Trident DI Issues - LOV: Pointed to CyberIntegrity inventory capability; noted current limitations in TRX component breakdown. | L1 Integrity, Alarm Rationalization | Low |  | Production