## Sheet1
Date | Issue | Investigation_Approach | Root_Cause | Resolution | Improvement_Made
last Friday | ISOM OPCI Channel Marginal (LAR16ISO-ACT110 faulted) | Reloaded ACE with correct sequence (ACT first, then CEE); manual troubleshooting across Experion patching context | Experion patching caused ACE fault; non-redundant ACE hosting NTEs | Reloaded ACE modules in correct order; restored normal state | Identified sequencing requirement; flagged patching risk for future maintenance
Feb 14, 2025 | Integrity global search failure after upgrade | Multi-day upgrade attempt; SQL permissions fix; vendor confirmation pending | SQL permissions misconfiguration during upgrade | Completed upgrade; bug fixed; ticket closed | Documented upgrade steps; improved permission validation process
May 1, 2025 | Dashboard license error (Integrity) | Checked BLAN vs application; validated license state | User error (license update unnecessary for normal use) | Updated license; cleared error; closed ticket | Added clarification in SOP to prevent similar confusion
Jan 6, 2026 | ETD_UTIL Tag Sync anomalies | Compared TagSync logs; analyzed Preview vs Active modes; timeline correlation | Retained timestamp from earlier Preview sync; caused Proposed state mismatch | Disabled scheduled task; corrected sync mode; tags added properly | Recommended notification feature for TagSync failures; improved monitoring
last Tuesday | Missing tags in ACM (Crude Migration Transfer) | Reviewed TagSync logs across Feb–May; traced undelete limitations | Tags marked deleted in ACM prevented re-addition; no undelete functionality | Manual restore of impacted tags; validated alarm help import | Suggested enhancement for TagSync notifications; flagged undelete gap for vendor
last Thursday | ACM DB corruption – Alarm Help loss on re-import | Provided detailed reproduction steps; escalated TAC SR; multi-week investigation | Improper handling of Line Feed characters during import | Vendor acknowledged bug; fix applied; SR closed | Shared lessons learned; proposed Honeywell process improvement for SR handling