## Executive Summary
Section | Description
⚠️ TOP REASONS FOR DELAYS & COST OVERRUNS | Based on Marathon Petroleum pilots and multiple site assessments
1. MISUNDERSTANDING OF DEPENDENCIES | Delays and additional costs
• | Perception that APO and Reporting must be deployed together
• | Actually: HAMR should be working well (HAMR 2.3.0+) BEFORE APO
• | Critical to have hierarchies compatible across ACM/M&R/EAS
2. LICENSE MISCALCULATION | Cost overruns, delays if license insufficient
• | Cannot delete tags without licenses - no reclaim after ordering
• | Too many licenses bought but cannot return excess
• | Example: Anacortes reduced by 35% through cleanup
• | License count during migration unreliable but allows proceed
3. IT-FOCUSED PROJECTS (Quality & Usability Ignored) | No focus on quality or usability
• | Optimal configuration gets insufficient attention
• | Delays in providing functional enhancements
• | Custom solutions not prioritized
4. NO PRE-MIGRATION CLEANUP | Delays and ineffective outcomes
• | Hierarchy cleanup required (may take months)
• | Database cleanup and testing (months of work)
• | Corruptions must be fixed in ACM then re-migrate
• | Difficult to adjust hierarchies later in APO
• | Cannot realize full rationalization benefits without quality data
5. APO MATURITY GAPS | Missing features and functionality gaps
• | Custom solutions required for operational excellence
📊 CRITICAL SUCCESS FACTORS | Critical factors for successful migration
Database Health | ACM/HAMR cleanup, ghost tag removal, corruption fixes
License Sizing | Evaluate actual current usage before ordering (30-40% ghost tags common)
Hierarchy Alignment | Ensure ACM/M&R/EAS hierarchies aligned before migration
Custom Solutions | Plan for ACM→APO feature gaps, implement enhanced sync and tools
Training & Change Management | Focus on "what was lost" not just new features
Post-Migration Support | Daily health checks, backup/recovery, continuous improvement

## Pre-Assessment
# | Task | Owner | Status | Notes | Prerequisites
1. | Assessment Tasks
**4.1.1 ACM Database Quality Audit**
1.1 | Assessment checklist: | Site | ☐ Not Started
1.2 | Invalid tags (tags not in DCS) | Site | ☐ Not Started
1.3 | Ghost tags (historical tags no longer active) | Site | ☐ Not Started
1.4 | Tags in wrong assets (hierarchy misalignment) | Site | ☐ Not Started
1.5 | Corrupted parameters (invalid alarm limits, units, priorities) | Site | ☐ Not Started
1.6 | SCADA tags requiring cleanup | Site | ☐ Not Started
1.7 | Duplicate tags and naming inconsistencies | Site | ☐ Not Started
1.8 | Corrupted notes | Site | ☐ Not Started
1.9 | Tag description accuracy and completeness | Site | ☐ Not Started
1.10 | Alarm Help configuration dependencies | Site | ☐ Not Started
1.11 | Active enforcement mappings | Site | ☐ Not Started
1.12 | Dynamic mode enforcement configurations | Site | ☐ Not Started
1.13 | Health check methodology | Site | ☐ Not Started
1.14 | Tools and queries for assessment | Site | ☐ Not Started
1.15 | Validate ACM Consoles can map APO Consoles to HAMR Operating Positions | Site | ☐ Not Started
1.16 | Scoring system: Green/Yellow/Red health status | Site | ☐ Not Started
**4.1.2 M&R (Metrics & Reporting) Database Assessment**
1.17 | License consumption analysis: | Site | ☐ Not Started
1.18 | Identifying ghost tags (no events in M&R) | Site | ☐ Not Started
1.19 | Tag merging opportunities (e.g., History Index 200, 201, 202...) | Site | ☐ Not Started
1.20 | Case study: 10,000+ tag spike from invalid Redirection Index tags | Site | ☐ Not Started
1.21 | Old/corrupted assets removal | Site | ☐ Not Started
1.22 | Path re-arrangements and optimization | Site | ☐ Not Started
1.23 | Adjustments of Operating Positions for APO\ACM Console mapping | Site | ☐ Not Started
1.24 | Unassigned process assets should be addressed | Site | ☐ Not Started
1.25 | Performance improvement opportunities: | Site | ☐ Not Started
1.26 | Closing invalid alarms in database | Site | ☐ Not Started
1.27 | Removing invalid suppressed states | Site | ☐ Not Started
1.28 | Merging tag descriptions | Site | ☐ Not Started
1.29 | Retention period review and adjustment | Site | ☐ Not Started
**4.1.3 EMDB Integrity Verification**
1.30 | EAS EMDB quality assessment | Site | ☐ Not Started
1.31 | Automatic comparison tools (identifying discrepancies) | Site | ☐ Not Started
1.32 | Common EMDB issues discovered: | Site | ☐ Not Started
1.33 | Inconsistent naming conventions | Site | ☐ Not Started
1.34 | Orphaned assets | Site | ☐ Not Started
1.35 | Incorrect hierarchies | Site | ☐ Not Started
1.36 | Duplicate paths | Site | ☐ Not Started
1.37 | Cleanup and consolidation procedures | Site | ☐ Not Started
**4.2.1 Tag-Level Issues**
1.38 | Non-alarmable tags: Tags that don't meet alarm definition (ISA 18.2) | Site | ☐ Not Started
1.39 | Invalid tag structures: Tags that will fail migration validation | Site | ☐ Not Started
1.40 | Tags not in DCS: Historical or test tags still in database | Site | ☐ Not Started
1.41 | Tag description quality: Incomplete, inaccurate, or missing descriptions | Site | ☐ Not Started
1.42 | Duplicate tags: Same physical point represented multiple times | Site | ☐ Not Started
1.43 | Tags in wrong assets: Misaligned with plant hierarchy | Site | ☐ Not Started
1.44 | BMA tags: Need to be removed prior migration, may need to mitigate with APO 3.1 | Site | ☐ Not Started
1.45 | Critical question: Will Honeywell provide a process? Or each customer needs to reinvent it? | Site | ☐ Not Started
**4.2.2 Parameter-Level Issues**
1.46 | Corrupted parameters: Invalid alarm limits, deadbands, delays | Site | ☐ Not Started
1.47 | Unit mismatches: Engineering units inconsistent between ACM and DCS | Site | ☐ Not Started
1.48 | Priority misalignment: Priorities not following rationalization rules | Site | ☐ Not Started
1.49 | Invalid time parameters: Response times and delay settings | Site | ☐ Not Started
1.50 | SCADA-specific corruptions: Common in SCADA tag integrations | Site | ☐ Not Started
1.51 | Notes corruption: May lose alarm help on re-import or notes look unprofessional | Site | ☐ Not Started
**4.3.1 M&R Database Assessment**
1.52 | Asset alignment: Ensuring ACM, M&R, and EAS EMDB consistency | Site | ☐ Not Started
1.53 | Path structure optimization | Site | ☐ Not Started
1.54 | New paths and reorganization opportunities | Site | ☐ Not Started
1.55 | Asset migration planning | Site | ☐ Not Started
1.56 | Addressing unassigned assets or incorrect assets assignments | Site | ☐ Not Started
**4.3.1 True License Requirement Calculation**
1.57 | Ghost tag identification and removal | Site | ☐ Not Started
1.58 | Invalid tag removal | Site | ☐ Not Started
1.59 | Merging consolidated tags | Site | ☐ Not Started
1.60 | License consumption projections | Site | ☐ Not Started
1.61 | Cost impact analysis | Site | ☐ Not Started
**4.3.2 License Ordering Strategy**
1.62 | CRITICAL: Cannot reclaim licenses after ordering | Site | ☐ Not Started
1.63 | Validation procedures before license order | Site | ☐ Not Started
1.64 | Contingency buffer (recommended: 5-10%) | Site | ☐ Not Started
1.65 | License type selection (permanent vs. term) | Site | ☐ Not Started
**4.4.1 Alarm Help Configuration**
1.66 | Alarm Help Router connections | Site | ☐ Not Started
1.67 | Alarm Help content dependencies | Site | ☐ Not Started
1.68 | Custom Alarm Help integrations | Site | ☐ Not Started
1.69 | Migration impact on Alarm Help availability | Site | ☐ Not Started
**4.4.2 Enforcement Dependencies**
1.70 | Static enforcement mappings | Site | ☐ Not Started
1.71 | Dynamic mode enforcements (highest risk) | Site | ☐ Not Started
1.72 | Console-specific enforcements | Site | ☐ Not Started
1.73 | "Reverse enforcement" scenarios (DCS is master) | Site | ☐ Not Started
1.74 | Example: Dead Band Units controlled only on DCS | Site | ☐ Not Started
1.75 | Custom enforcement rules requiring special handling | Site | ☐ Not Started
**4.4.3 Reporting and Integration Dependencies**
1.76 | M&R reporting schedules and dependencies | Site | ☐ Not Started
1.77 | Custom reports and dashboards | Site | ☐ Not Started
1.78 | Third-party system integrations | Site | ☐ Not Started
1.79 | Data exports and interfaces | Site | ☐ Not Started
**4.5.1 Establishing Temporary ACM Environment**
1.80 | Installing temporary Manager Server | Site | ☐ Not Started
1.81 | Installing temporary Enforcer Server (can be on client/station) | Site | ☐ Not Started
1.82 | Purpose: Allow cleanup without affecting production operations | Site | ☐ Not Started
1.83 | Maintaining Alarm Help and enforcement availability | Site | ☐ Not Started
**4.5.2 Step-by-Step ACM Cleanup**
1.84 | Corrupted notes | Site | ☐ Not Started
1.85 | Invalid parameters | Site | ☐ Not Started
**4.5.3 M&R Database Optimization**
1.86 | Hierarchy optimization | Site | ☐ Not Started
1.87 | Ghost tag removal procedures | Site | ☐ Not Started
1.88 | Asset cleanup and consolidation | Site | ☐ Not Started
1.89 | Performance optimization (closing invalid alarms, etc.) | Site | ☐ Not Started
1.90 | Retention adjustment implementation | Site | ☐ Not Started
**4.5.4 Validation and Quality Assurance**
1.91 | Pre-cleanup baseline metrics | Site | ☐ Not Started
1.92 | Post-cleanup validation | Site | ☐ Not Started
1.93 | Test enforcements and alarm help | Site | ☐ Not Started
1.94 | Reporting validation | Site | ☐ Not Started
1.95 | Sign-off criteria for migration readiness | Site | ☐ Not Started

## Cleanup
# | Task | Owner | Status | Notes | Prerequisites
1. | Cleanup Tasks
ACM Cleanup
1.1 | Remove ghost tags and orphaned entries | Site | ☐ Not Started
1.2 | Fix hierarchy corruptions | Site | ☐ Not Started
HAMR Cleanup
1.3 | Install HAMR 2.3.0+ before APO | Vendor | ☐ Not Started
1.4 | Remove ghost tags from HAMR database | Site | ☐ Not Started

## Custom-Solutions
# | Task | Owner | Status | Notes | Prerequisites
1. | Custom Solution Tasks
Gap Analysis
1.1 | Identify ACM→APO feature gaps | Site | ☐ Not Started
Custom Tools
1.2 | Develop tag export/import tools | Custom | ☐ Not Started
Health Checks
1.3 | Implement daily health check scripts | Custom | ☐ Not Started

## Pre-Planning
# | Task | Owner | Status | Notes | Prerequisites
1. | Installation Planning Tasks
**6.1.1 Infrastructure Requirements**
1.1 | Server specifications (APO Site Server, Transfer Service) | IT/OT | ☐ Not Started
1.2 | Network requirements (connectivity to DCS, database servers) | IT/OT | ☐ Not Started
1.3 | Storage requirements and growth planning | Site | ☐ Not Started
1.4 | Virtualization considerations | Site | ☐ Not Started
**6.1.2 SQL Server Configuration**
1.5 | SQL Server version requirements (compatibility matrix) | IT/OT | ☐ Not Started
1.6 | Database sizing and performance tuning | Site | ☐ Not Started
1.7 | SQL permissions and service accounts | IT/OT | ☐ Not Started
1.8 | SQL Server properties | IT/OT | ☐ Not Started
1.9 | Transaction log management | Site | ☐ Not Started
1.10 | Backup infrastructure | IT/OT | ☐ Not Started
**6.1.3 Organizational Standards**
1.11 | Schema naming conventions (consistency across sites) | Site | ☐ Not Started
1.12 | Folder structures and file organization | Site | ☐ Not Started
1.13 | Service account naming and management | Site | ☐ Not Started
1.14 | Security group assignments | Site | ☐ Not Started
1.15 | Documentation standards | Site | ☐ Not Started
**6.1.4 Network and Security**
1.16 | Firewall rules and port requirements | Site | ☐ Not Started
1.17 | Certificate management (SSL/TLS) | Site | ☐ Not Started
1.18 | Domain trust relationships | Site | ☐ Not Started
1.19 | OT security compliance | Site | ☐ Not Started
**6.2.1 Following Organizational Standards During Install**
1.20 | Standard installation checklists | Site | ☐ Not Started
1.21 | Standard naming conventions | Site | ☐ Not Started
1.22 | Standard configurations | Site | ☐ Not Started
1.23 | Configuration management approach | Site | ☐ Not Started
1.24 | As-built documentation requirements | Site | ☐ Not Started
**6.2.2 Database Creation and Migration**
1.25 | APO database creation procedures | Site | ☐ Not Started
1.26 | ACM to APO data migration process | Site | ☐ Not Started
1.27 | Validation of migrated data | Site | ☐ Not Started
**6.2.3 Asset Migration Approach**
1.28 | EMDB to APO asset structure mapping | Site | ☐ Not Started
1.29 | Hierarchy recreation and validation | Site | ☐ Not Started
1.30 | Console assignment | Site | ☐ Not Started
**6.2.4 System Configuration**
1.31 | Site settings and preferences | Site | ☐ Not Started
1.32 | User authentication (Active Directory integration) | Site | ☐ Not Started
1.33 | Role-based access control (RBAC) setup | Site | ☐ Not Started
1.34 | Notification configuration (email alerts, etc.) | Site | ☐ Not Started

## OSW-Completion
# | Task | Owner | Status | Notes | Prerequisites
1. | OSW Data Entry
Assets
1.1 | Complete Asset Hierarchy (Site→Area→Unit→System→Subsystem) | Site | ☐ Not Started
1.2 | Validate hierarchy matches FDS standards | Site | ☐ Not Started
Devices
1.3 | Complete Device Inventory (manufacturer, model, protocol) | Site | ☐ Not Started
1.4 | Classify external reference devices | Site | ☐ Not Started
1.5 | Document unsupported devices with justification | Site | ☐ Not Started
2. | External Reference Configuration
ControlLogix
2.1 | Provide .L5X/.L5K export and I/O config | Site | ☐ Not Started
PLC5/SLC
2.2 | Provide .RSS export and addressing scheme | Site | ☐ Not Started
Triconex
2.3 | Confirm EPKS External Reference or TPS import | Site | ☐ Not Started
Bently Nevada
2.4 | Confirm DCS External Reference method | Site | ☐ Not Started
Analyzers
2.5 | Decide manual entry vs automated import | Site | ☐ Not Started
3. | OSW Validation
Review
3.1 | Vendor reviews OSW for completeness | Vendor | ☐ Not Started
3.2 | Site confirms all devices in scope | Site | ☐ Not Started
3.3 | ⚠️ NO additions after sign-off without Change Order | Site | ☐ Not Started
Sign-Off
3.4 | Executive sponsor signs off (scope locked) | Site | ☐ Not Started

## Deployment-Readiness
# | Task | Owner | Status | Notes | Prerequisites
1. | Readiness Tasks
**6.3.1 APO R3.0.0 Migration Utility Usage**
1.1 | Migration utility features and capabilities | Site | ☐ Not Started
1.2 | Pre-migration validation checks | Site | ☐ Not Started
1.3 | Migration utility configuration | Site | ☐ Not Started
1.4 | Execution and monitoring | Site | ☐ Not Started
**6.3.2 Three-Phase Migration Approach**
1.5 | Phase 1: Pre-migration | Site | ☐ Not Started
1.6 | Configure essential components | Site | ☐ Not Started
1.7 | Secure site environment | Site | ☐ Not Started
1.8 | Validate prerequisites | Site | ☐ Not Started
1.9 | Validate quality of data | Site | ☐ Not Started
1.10 | Phase 2: Migration | Site | ☐ Not Started
1.11 | Validate source data | Site | ☐ Not Started
1.12 | Map assets and tags | Site | ☐ Not Started
1.13 | Execute migration utility | Site | ☐ Not Started
1.14 | Monitor progress | Site | ☐ Not Started
1.15 | Phase 3: Post-migration | Site | ☐ Not Started
1.16 | Conduct data integrity reviews | Site | ☐ Not Started
1.17 | Validation tools execution | Site | ☐ Not Started
1.18 | Reconciliation reports | Site | ☐ Not Started
1.19 | Validate quality of data | Site | ☐ Not Started
**6.3.3 Data Transformation and Mapping**
1.20 | Tag attribute mapping (ACM to APO) | Site | ☐ Not Started
1.21 | Priority translation | Site | ☐ Not Started
1.22 | Alarm type conversions | Site | ☐ Not Started
1.23 | Custom field mapping | Site | ☐ Not Started
**6.3.4 Error Handling and Resolution**
1.24 | Common migration errors and causes | Site | ☐ Not Started
1.25 | Error log analysis | Site | ☐ Not Started
1.26 | Remediation procedures | Site | ☐ Not Started
1.27 | When to restart vs. fix-forward | Site | ☐ Not Started
**6.3.5 Data Integrity Verification**
1.28 | Tag count reconciliation | Site | ☐ Not Started
1.29 | Asset structure validation | Site | ☐ Not Started
1.30 | Alarm limit verification | Site | ☐ Not Started
1.31 | Enforcement mapping confirmation | Site | ☐ Not Started
1.32 | Sample testing approach | Site | ☐ Not Started
**6.4.1 Running ACM and APO Concurrently**
1.33 | Infrastructure for parallel operations | Site | ☐ Not Started
1.34 | Data synchronization strategy | Site | ☐ Not Started
1.35 | Avoid OPC overload \ overlapping tasks (enforcements, tagsync) | Site | ☐ Not Started
1.36 | Operator interface management (which system is primary?) | Site | ☐ Not Started
**6.4.2 Critical Considerations for Enforcements**
1.37 | Static enforcements: Parallel operation approach | Site | ☐ Not Started
1.38 | Dynamic mode enforcements: High-risk scenarios | Site | ☐ Not Started
1.39 | Testing enforcements without impacting DCS | Site | ☐ Not Started
1.40 | Enforcement cutover planning | Site | ☐ Not Started
**6.4.3 Conflict Resolution Procedures**
1.41 | Change request management during parallel operations | Site | ☐ Not Started
1.42 | Which system is source of truth? | Site | ☐ Not Started
1.43 | Merging changes from both systems | Site | ☐ Not Started
**6.4.4 Performance Monitoring**
1.44 | System resource utilization | Site | ☐ Not Started
1.45 | Response time monitoring | Site | ☐ Not Started
1.46 | Operator workload assessment | Site | ☐ Not Started

## Migration-Execute
# | Task | Owner | Status | Notes | Prerequisites
1. | Migration Execution Tasks
Execution
1.1 | Run ACM to APO migration tool | Vendor | ☐ Not Started
1.2 | Validate data transfer completeness | Vendor | ☐ Not Started
Configuration
1.3 | Configure APO site settings | Site | ☐ Not Started

## Validation
# | Task | Owner | Status | Notes | Prerequisites
1. | Parallel Operation Setup
Configuration
1.1 | Run ACM and APO in parallel (30-90 days) | Site | ☐ Not Started
1.2 | Maintain ACM for fallback capability | Site | ☐ Not Started
1.3 | Monitor both systems for discrepancies | Site | ☐ Not Started
2. | Data Validation
Testing
2.1 | Compare ACM and APO alarm counts | Site | ☐ Not Started
2.2 | Validate enforcement execution | Site | ☐ Not Started
2.3 | Verify reporting accuracy | Site | ☐ Not Started
2.4 | Test custom solutions in APO | Custom | ☐ Not Started
3. | Performance Validation
Metrics
3.1 | Monitor sync accuracy (Standard vs Alternative) | Site | ☐ Not Started
3.2 | Verify KPI calculations match ISA 18.2 requirements | Site | ☐ Not Started
3.3 | Validate daily health check notifications | Custom | ☐ Not Started

## Cutover
# | Task | Owner | Status | Notes | Prerequisites
1. | Pre-Cutover
Validation
1.1 | Final ACM vs APO comparison | Site | ☐ Not Started
1.2 | ⚠️ CRITICAL: Confirm all enforcements tested | Site | ☐ Not Started
1.3 | Document any known issues and workarounds | Site | ☐ Not Started
Communication
1.4 | Notify operations of cutover schedule | Site | ☐ Not Started
2. | Cutover Execution
Cutover
2.1 | Disable ACM enforcements | Site | ☐ Not Started
2.2 | Enable APO enforcements | Site | ☐ Not Started
2.3 | Monitor first 24 hours closely | Site | ☐ Not Started
2.4 | Verify DCS and APO in sync | Site | ☐ Not Started
3. | ACM Decommission
Decommission
3.1 | Retain ACM for 90 days as backup | Site | ☐ Not Started
3.2 | Archive ACM database | Site | ☐ Not Started
3.3 | Remove ACM services (after approval) | IT/OT | ☐ Not Started

## Post-Migration
# | Task | Owner | Status | Notes | Prerequisites
1. | Optimization Tasks
**7.5.1 Regular Database Maintenance**
1.1 | Weekly maintenance tasks | Site | ☐ Not Started
1.2 | Monthly optimization activities | Site | ☐ Not Started
1.3 | Quarterly health assessments | Site | ☐ Not Started
**7.5.2 License Optimization (Ongoing)**
1.4 | Ghost tag monitoring and removal | Site | ☐ Not Started
1.5 | License consumption trending | Site | ☐ Not Started
1.6 | Optimization opportunities identification | Site | ☐ Not Started
**7.5.3 Performance Tuning**
1.7 | Query optimization | Site | ☐ Not Started
1.8 | Index maintenance | Site | ☐ Not Started
1.9 | Resource utilization monitoring | Site | ☐ Not Started
**7.5.4 User Feedback Incorporation**
1.10 | Regular operator surveys | Site | ☐ Not Started
1.11 | Usability improvement initiatives | Site | ☐ Not Started
1.12 | Feature request tracking | Site | ☐ Not Started