## Executive Summary DELETE
HEXAGON INTEGRITY DEPLOYMENT - EXECUTIVE SUMMARY
Critical Success Factors for Site Readiness
Based on lessons learned from Marathon Petroleum multi-site deployments (ROB, LAR, GBR, SPP, GVL, SLC)
🎯 PROJECT OBJECTIVES
• Centralized control system configuration management across all refinery assets
• Enable cross-system signal tracing (PLC → DCS → Safety → Monitoring)
• Establish single pane of glass enterprise dashboard (L5 visibility)
• Maintain asset integrity while implementing standardized hierarchies
⚠️ TOP REASONS FOR DEPLOYMENT DELAYS & COST OVERRUNS
1. INCOMPLETE DATA COLLECTION (60% of delays)
• Missing L1 inventories (Relays, Vibration Monitoring, Analyzers not tracked by Process Control)
• Stakeholders engaged AFTER OSW sign-off instead of during planning
• Programs/backups not accessible on workstations when consultant arrives
→ IMPACT: 3-6 week delays, $50K-$100K rework per site
2. SCOPE CHANGES AFTER OSW SIGN-OFF (30% of cost overruns)
• Example: GBR added 1,614 new assets requiring complete database rebuild
• Asset hierarchy changes discovered during deployment (Area/Domain mismatches)
• Quote: "We were not informed about this project" - GBR site personnel
→ IMPACT: $20K-$75K per scope change, 2-4 week schedule delays
3. DATA MOVEMENT INFRASTRUCTURE NOT READY (20% of delays)
• L1→L2→L4 automated transfer not configured before deployment
• Server permissions/accounts not established
• SQL backup/restore not tested
→ IMPACT: Deployment cannot start, 1-3 week delays
4. TECHNICAL PREREQUISITE GAPS (15% of issues)
• Carbon Black blocking Hexagon utilities
• Missing vendor software/licenses on workstations
• Network architecture undecided (Azure migration, server locations)
→ IMPACT: Consultant idle onsite, $10K-$30K wasted travel costs
💰 FINANCIAL PERFORMANCE
Marathon Program (Dec 2025): Budget Spent 43.8% ¦ Work Complete 27.4% ¦ CPI 0.62
Translation: Spending $1.00 to get $0.62 worth of work
Primary Cost Drivers: Re-work ($900/hr) + Pre-work ($275/hr) + Deviations ($275-900/hr)
Sites with BEST Performance: Complete OSW before sign-off + Remote deployment + Single contact
Savings: $15K-$25K travel per site when remote deployment used
✅ CRITICAL SUCCESS FACTORS - DO THESE FIRST
BEFORE OSW (3-4 weeks lead time):
1. Designate Site Lead (20% FTE, 6-8 weeks)
2. Engage ALL stakeholders: Process, Reliability, Electrical, IT/OT
3. Complete L1 inventory (use template)
4. Verify programs accessible
DURING OSW (2-3 weeks):
5. Answer Hexagon questions within 48-72 hours
6. Validate hierarchies match FDS standards
7. Classify supported vs unsupported devices
8. Executive sign-off: No additions after OSW
BEFORE DEPLOYMENT (1-2 weeks):
9. Complete Onsite Readiness 100%
10. Test L1→L4 data movement with fresh data
11. Establish accounts and grant access
12. Schedule SME availability
📋 HOW TO USE THIS CHECKLIST
Phase 1 - Pre-Planning (Week -4 to -1)
Phase 2 - OSW Completion (Week 1-3)
Phase 3 - Deployment Readiness (Week 4-5)
Phase 4 - Data Collection (Week 6-8)
Phase 5 - Validation & Go-Live (Week 9-10)
Each checklist tab includes:
• Task description with clear accountability
• Owner (Site/Hexagon/IT) color-coded
• Status tracking column
• Notes for issues/decisions
• Prerequisites showing dependencies
🎓 LESSONS LEARNED QUOTES
"Ad-hoc model is not suited for such projects. GBR and SPP are examples of what NOT to do when planning. ROB is an example of what NOT to do when executing."
- Hexagon Delivery Manager, November 2025
"If after sign-off the site adds more scope, it will lead to Change Orders and cost Marathon more money."
- Repeated in Multiple Status Meetings
📞 SUPPORT
Marathon: Keith Mazy, Don Clark (lar-integrityrequests@marathonpetroleum.com)
Hexagon PM: (assigned during kickoff)
Corporate IT: (Infrastructure team)
Version 2.0 - Enhanced for Multi-Site Deployment (January 2026)

## Executive Summary
# |  | APO DEPLOYMENT - EXECUTIVE SUMMARY
Critical Success Factors for Site Readiness
Based on APO Test System evaluation, APO1.0 deployment, and the quality of ACM and HAMR reviews at several sites
⚠️ TOP REASONS FOR DEPLOYMENT DELAYS & COST OVERRUNS & BAD OUTCOMES
0
1 | MISUNDERSTANDING OF DEPENDENCIES (delays, costs)
2 | • | Perception APO and Reporting have to be deployed together
2 | • | In fact Important to have Reporting working well (HAMR230 recommended) before APO deployment
2 | • | Critical to have hierarchies compatible
2 | LICENSE MISCALCULATION (cost, delays if need higher license)
3 | • | Apears you cannot delete (deleted) tags without buying licencese to re-enable delete functionality
3 | • | Too many licenses bougth, cannot return
3 | • | Anacortes - cleanup and license reduction by 35%
3 | • | License count shown during migration not reliable (and allows to proceed if insufficient)
3 | PROJECTS ARE PLANED AND DECLARED COMPLETE MOSTLY FROM IT PERSPECTIVE
4 | • | No focus on quality or usability
4 | • | Optimal configuration does not get sufficient attention
4 | • | Delays in providing functional enhancements
4 | •
4 | NO CLEANUP (delays, ineffective outcome)
5 | • | Hierarchy cleanup
5 | • | Databases cleanup (cleanup and testing can take months)
5 | • | Corruptions
5 | • | May need to go back to ACM to clean, then redo migration
| • | Difficult to adjust hierarchies later (and clean data) considering APO is "rationalization tool where enforcements were recently added but no full ACM functionality is avaiable yet.
5 | • | Not able to realize full APO rationalization benefits withouth well designed hierarchies and quality data
5 | APO STILL IMMATURE FOR MAJOR ADJUSTMENTS
6 | • | APO 1.1 lack of management tools made LAR Wilmington not operational for months
6 | • | Need to organize and clean data in ACM to minimize the risks
6 | • | APO focus was and is rationalization, alarm management \ maintenance functionality clearly lower priority for Honeywell
6 | INEXPERIENCED VENDOR RESOURCES (no senior resources)
7 | • | No effective understanding of functionalities and possible adjustments
7 | • | No deep Health Checks (e.g. channel is green assumes HAMR is working)
7 | • | Even proper Validation ensures only "Software works" but not "software works well and configuration is optimized"
7 | • | Adjust expectations and mitigate knowledge gaps, it will take time for Honeywell to train new engineers
7 | •
7 | •
7 | LACK OF EFFECTIVE BACKUP PROCEDURES
8 | • | Vendor instructions do not ensure deterministic\reliable restore of multiple databases and files
8 | • | Data loss
8 | • | Data corruptions
8 | •
8 | UPGRADES DAMAGE FUNCTIONALITY (not immediately noticable)
9 | • | Some may be not directly noticable, but affect quality (e.g. MnR Sync)
9 | • | Replication can be damaged and work inconsistently or not allow to upgrade standard way
9 | • | Need for functionality\data Health Checks (vs. IT conclusion "Software runs")
9 | LACK OF AUTO-MONITORING - issues not noticed for months or years
10 | • | Garyville, wrong archive were restored (with high EventIDs) and collection stoped for months. Hourly Active Sync did not make the failure obvious.
10 | • | Anacortes, collection stalled for 10 months, not noticed due to frequent Active Sync (every 4 hours)
10 | • | LAR: collection stalled, notification allowed to detect and solve timely
10 | • | These incomplete collections are loaded to APO and wrong recommendations are issued
10 | Lack of deployment standards will make custom Marathon functionality difficult to standarize
11 | • | Custom functionality not well standarized for full Marathon (example OL)
11 | •
11 | Lack of good documentation post install
12 | • | Need for short, ONE PAGE documentation with major info (details separately unless unusual)
12 | • | With standards… documentation non-critical
12 | •
12 | Testing scope
13 | • | Neeed for standarized basic tests\expectation (and higher level of data quality validation)
13 | • | Test not enough (checks only "Software installed and basics works")… Quality Health Check needed
13 | •
13 | L4 Server Delays and restrictions (SQL Azure restrictions)
14 | • | Still analyzing
| • | Lack of control over L4 should not be the basis for the decisions to install APO on L4 (e.g. uncoordinated patching \ reboots)
14 | RISK OF ACCITENTAL ENFORCEMENTS OR OPC OVERLOAD
15 | • | Should be top priority to avoid this during the process
15 | •
15 | •
15 | •
15 | •
15 | •
15 | •
15 | •
15 | •
15 | •
15 | •
15 | •
15
15
15
6

## Follow Up
# | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Current SRs
2 | 1 | SCADA SRs | Vendor
2 | 2
2 | 3
2 | 4
2 | 5
2 | SRs to consider
3 | 6 | Migration - Carson hierarchy migration fails | Vendor
3 | 7 | Over the license… how to delete tags | Custom
3 | 8 | How to export\import EMDBs | Custom
3 | 9 | Import \ Export missed | Custom
3 | 10 | Stuck enforcement (?), appears got stuck on Test system | Custom
| 11 | Backup \ Restore how to? | Custom
| 12 | How to re-release all tags? | Vendor
3 | 13 | Where schedules are stored?
3 | 14
3 | Suggestions
4 | 15 | You know before users notice
4 | 16
4 | 17
4 | 18
4 | 19
4 | 20
4 | Questions
5 | 21 | Do we have edge in stations? IE not working any more
5 | 22
5 | 23
5 | 24
5 | 25
5 | 26
Site
IT\OT
Vendor
Custom

## 0-Cleanup (Pre-license)
# | Item # | Task | Owner | Status | Notes | Prerequisites | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Stakeholder Engagement & Project Setup | [5 empty] | 1. Stakeholder Engagement & Project Setup
2 | 1 |  | Site |  |  |  | 1 | Identify and engage Site Lead (20% FTE, 6-8 week commitment) | Site
2 | 2 | [5 empty] | 2 | Schedule kickoff meeting with Process Control, Reliability, Electrical, IT/OT stakeholders | Site |  |  | 1
2 | 3 | [5 empty] | 3 | Brief stakeholders on Integrity purpose, scope, timeline, and data requirements | Hexagon |  |  | 2
2 | 4 | [5 empty] | 4 | Establish weekly status meeting cadence with consistent attendees | Site |  |  | 2
2 | 5 | [5 empty] | 5 | Designate single point of contact for Hexagon questions (48-72hr response SLA) | Site |  |  | 1
2 | Minimum Releases Upgrade and additional ACM server | [5 empty] | 2. L1 Inventory & Device Discovery
3 | 6 | M&R 210 or higher, HAMR230 recommended | Site |  |  |  | 6 | Complete L1 inventory template (DCS, PLC, Safety, Historian, Analyzers, Relays) | Site |  |  | 2
3 | 7 | ACM 210.12.7 or higher (SCADA UTT or 321.12.8) | Site |  |  |  | 7 | Identify devices NOT managed by Process Control (Reliability, Electrical assets) | Site |  |  | 2,7
3 | 8 | Dedicated station for ACM TEST server | Site |  |  |  | 8 | Document network architecture (L1→L2→L4→L5) with IP ranges and VLANs | IT/OT |  |  | 2
3 | 9 | Process to Copy production to Test server (with NO schedules) | Custom |  |  |  | 9 | Verify all L1 devices accessible from designated L2 workstation | Site |  |  | 8
3 | 10 | Auto process to avoid accidental enforce and OPC overload |  |  |  |  | 10 | Identify unsupported devices (Honeywell TDC2000, Foxboro I/A, obsolete systems) | Site |  |  | 7,8
3 | 11 | [5 empty] | 11 | Document external reference systems (Allen-Bradley, Triconex, Bently Nevada) | Site |  |  | 7,8
3 | Synchronized Backups to ensure deterministic restore | [5 empty] | 3. Program Accessibility Verification
4 | 12 | Files | Custom |  |  |  | 12 | Verify DCS backup files accessible (EPKS: .bak, .bkp, .stn) | Site |  |  | 4
4 | 13 | DBs | Custom |  |  |  | 13 | Verify PLC programs accessible (RSLogix .ACD/.RSS, Control Studio) | Site |  |  | 4
4 | 14 | Exports of EMDB | Custom |  |  |  | 14 | Verify Safety system exports available (Triconex, Safety Manager) | Site |  |  | 4
4 | 15 | Export of ACM all consoles | Custom |  |  |  | 15 | Verify Historian configuration exports (PHD, OSIPi) | Site |  |  | 4
4 | 16 | Purge to keep ~6 months | Site |  |  |  | 16 | Document program versions and last backup dates | Site |  |  | 12-15
4 | 17 | [5 empty] | 17 | Test restore/open programs on workstation to confirm readability | Site |  |  | 12-15
4 | Hierarchies Discovery Comparisons and adjustments | [5 empty] | 4. Installation Decision (Onsite vs Remote)
5 | 18 | All EMDBs | Site |  |  |  | 18 | Assess site network security and remote access capability | IT/OT |  |  | 3,8
5 | 19 | OL Hierarchy | Site |  |  |  | 19 | Evaluate travel cost ($15K-$25K) vs security/policy constraints | Site |  |  | 3
5 | 20 | HAMR Hierarchy (likely cache regen required) | Site |  |  |  | 20 | If onsite: Reserve consultant workspace and schedule site access badging | Site |  |  | OSW complete
5 | 21 | Consider M&R OP name: Area - Unit (helps with OL hierarchy) | Site |  |  |  | 21 | If remote: Validate VPN/remote desktop performance with test session | IT/OT |  |  | 3,8,23
5 | 22 | ACM Hierarchy | Site |  |  |  | 22 | Confirm Carbon Black/antivirus exceptions for Hexagon utilities | IT/OT |  |  | 23
5 | 23 | All hierarchies compatible | Site |  |  |  | 23 | Document decision in OSW with rationale | Site |  |  | All above
5 | ACM DB Health Check \Cleanup
6 | 24 | Run Tag Count script | Custom
6 | 25 | Tags in wrong assets
6 | 26 | CMs - delete if not used
6 | 27 | Corruptions (SCADA, notes)
6 | 28 | Inconsistent Enforcement Actions (not matching defaults)
6 | 29 | Review UnManaged Tags (list from M&R)
6 | 30 | Reconfig errors
6 | 31 | Reload may be the best to clean (reload on test servers) coordinate with production
6 | 32 | For sites with no enforcement, prepare import file with only notes
6 | 33 | Optionally can switch to ReportOnly (if no life enforcements)
6 | 34 | Delete Offline or EHAS (unless you need them)
6 | 35 | At the end… freeze and delta migration (logs and settings)
6 | 36 | Move clean ACM DB to Production
6 | ACM review \ adjust site \Control System\Console settings
7 | 37 | There are common recommendations (e.g. auto assigne tag to parent asset)
7 | Any outstanding import files… import now
8 | 38 | These files are not valid for APO any more | Site
8 | ACM TagSync
9 | 39 | Schedule all tasks (Add\Delete + Reconfig can be in preview)
9 | 40 | [Add\Delete] - update MapFile.csv
9 | 41 | [Add\Delete] - update ExclusionList.txt
9 | 42 | [Add\Delete] - nonEmpty add + delete list
9 | 43 | [Update Sec Param] check in M&R is there is Tag Descrption mismatch
9 | 44 | Run DSPPrime for Tag Descriptio mismatches
9 | 45 | [Reconfig]: The file should be empty
9 | 46 | Considering you have test system, the best may be to reload
9 | ACM review over time
10 | 47 | Unmananaged tags need to be added to ACM
10 | M&R DB Health Check \ Cleanup
11 | 48 | Adjust purge (12 months recommended)
11 | 49 | No Unassigned Process Asset (with alarms)
11 | 50 | No Ghost Tags
11 | 51 | No Tags to merge
11 | 52 | Rules updated to prevent excessive Tags (when tags should be merged)
11 | 53 | Quality: Consider Alternative Active and Suppressed Sync
11 | 54 | Standard Sync no quality and mostly not configured right
11 | 55 | Quality: Active Alarms
11 | 56 | Active Sync generally should not add alarms\shelved (only close them)
11 | 57 | Quality: Suppressed Tags
11 | 58 | Suppressed Sync should mostly unsuppress
11 | 59 | Monitor Report generation (Inactive report SLC has seen seeing IOL Overrun errors)
11 | 60 | For unassigned assets and DSA events, consider rules adjustments
11 | 61 | Cosider Alarm Class implementation (info entered in ACM)
11 | M&R Sync and rules adjustments over time
12 | 62 | Unassigned assets over DSA need rules adjustmenst to ensure quality
12 | Ensure Backups are running and tested
13 | 63 | Test Backups
13 | License needs evaluation
14 | 64 | Assumes cleanup done
14 | 65 | ACM count tags + 15% if not significant tag count growth expected | Custom
14 | 66 | M&R count tags + 15% if not significant tag count growth expected | Custom
14 | 67
14 | 68
14 | 69
14 | xxx
15 | 70
15 | 71
15 | 72
15 | 73
15 | 74
15 | 75
Site
IT\OT
Vendor
Custom

## 1-Custom Solutions
# | Item # | Task | Owner | Status | Notes | Prerequisites | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Marathon Custom solutions | [5 empty] | 1. Stakeholder Engagement & Project Setup
2 | 1 | OL Solution (replication may be needed if L3 install) | Site |  |  |  | 1 | Identify and engage Site Lead (20% FTE, 6-8 week commitment) | Site
2 | 2 |  | IT\OT |  |  |  | 2 | Schedule kickoff meeting with Process Control, Reliability, Electrical, IT/OT stakeholders | Site |  |  | 1
2 | 3 |  | Vendor |  |  |  | 3 | Brief stakeholders on Integrity purpose, scope, timeline, and data requirements | Hexagon |  |  | 2
2 | 4 |  | Custom |  |  |  | 4 | Establish weekly status meeting cadence with consistent attendees | Site |  |  | 2
2 | 5 | [5 empty] | 5 | Designate single point of contact for Hexagon questions (48-72hr response SLA) | Site |  |  | 1
2 | Custom effective backups | [5 empty] | 2. L1 Inventory & Device Discovery
3 | 6 | Vendor does not provide backup procedure that would ensure reliable restore | Custom |  |  |  | 6 | Complete L1 inventory template (DCS, PLC, Safety, Historian, Analyzers, Relays) | Site |  |  | 2
3 | 7 | While the criticality and scripts documented in KB, new engineers are not implementing | Custom |  |  |  | 7 | Identify devices NOT managed by Process Control (Reliability, Electrical assets) | Site |  |  | 2,7
3 | 8 | [5 empty] | 8 | Document network architecture (L1→L2→L4→L5) with IP ranges and VLANs | IT/OT |  |  | 2
3 | 9 | [5 empty] | 9 | Verify all L1 devices accessible from designated L2 workstation | Site |  |  | 8
3 | 10 | [5 empty] | 10 | Identify unsupported devices (Honeywell TDC2000, Foxboro I/A, obsolete systems) | Site |  |  | 7,8
3 | 11 | [5 empty] | 11 | Document external reference systems (Allen-Bradley, Triconex, Bently Nevada) | Site |  |  | 7,8
3 | Notifications | [5 empty] | 3. Program Accessibility Verification
4 | 12 | You know before users notice |  |  |  |  | 12 | Verify DCS backup files accessible (EPKS: .bak, .bkp, .stn) | Site |  |  | 4
4 | 13 | [5 empty] | 13 | Verify PLC programs accessible (RSLogix .ACD/.RSS, Control Studio) | Site |  |  | 4
4 | 14 | [5 empty] | 14 | Verify Safety system exports available (Triconex, Safety Manager) | Site |  |  | 4
4 | 15 | [5 empty] | 15 | Verify Historian configuration exports (PHD, OSIPi) | Site |  |  | 4
4 | 16 | [5 empty] | 16 | Document program versions and last backup dates | Site |  |  | 12-15
4 | 17 | [5 empty] | 17 | Test restore/open programs on workstation to confirm readability | Site |  |  | 12-15
4 | Major Gaps bridge - My need custom solutions. | [5 empty] | 4. Installation Decision (Onsite vs Remote)
5 | 18 | No import \ export | Site |  |  |  | 18 | Assess site network security and remote access capability | IT/OT |  |  | 3,8
5 | 19 | No EMDB import \ export (and easy manipulation) - Only Export to Excel Rationalization Tool | Site |  |  |  | 19 | Evaluate travel cost ($15K-$25K) vs security/policy constraints | Site |  |  | 3
5 | 20 | No Tag Sync | Site |  |  |  | 20 | If onsite: Reserve consultant workspace and schedule site access badging | Site |  |  | OSW complete
5 | 21 | No BMA | Site |  |  |  | 21 | If remote: Validate VPN/remote desktop performance with test session | IT/OT |  |  | 3,8,23
5 | 22 | Still stuck enforcement? Or fixed? | Custom |  |  |  | 22 | Confirm Carbon Black/antivirus exceptions for Hexagon utilities | IT/OT |  |  | 23
5 | 23 | [5 empty] | 23 | Document decision in OSW with rationale | Site |  |  | All above
5 | Recomended settings ("custom" as not default)
6 | 24 | HAMR Rules \ Processing
6 | 25 | ACM Site Settings
6 | 26 | ACM Control System Settings
6 | 27 | ACM Console Settings
6 | 28 | ACM Priority Matrix
6 | 29
6 | Marathon Standards
7 | 30 | HAMR KPI Thresholds | Corporate
7 | 31 | Reports Scheduling for Corporate Marathon | Corporate
7 | 32
7 | 33
7 | 34
7 | 35
Site
IT\OT
Vendor
Custom

## 2-Pre-Planning
# | Item # | Task | Owner | Status | Notes | Prerequisites | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Stakeholder Engagement & Project Setup | [5 empty] | 1. Stakeholder Engagement & Project Setup
2 | 1 | Dedicated station for ACM install and all scripts | Site |  |  |  | 1 | Identify and engage Site Lead (20% FTE, 6-8 week commitment) | Site
2 | 2 |  | IT\OT |  |  |  | 2 | Schedule kickoff meeting with Process Control, Reliability, Electrical, IT/OT stakeholders | Site |  |  | 1
2 | 3 |  | Vendor |  |  |  | 3 | Brief stakeholders on Integrity purpose, scope, timeline, and data requirements | Hexagon |  |  | 2
2 | 4 |  | Custom |  |  |  | 4 | Establish weekly status meeting cadence with consistent attendees | Site |  |  | 2
2 | 5 | [5 empty] | 5 | Designate single point of contact for Hexagon questions (48-72hr response SLA) | Site |  |  | 1
2 | Order L4 server | [5 empty] | 2. L1 Inventory & Device Discovery
3 | 6 | L4 server | IT\OT |  |  |  | 6 | Complete L1 inventory template (DCS, PLC, Safety, Historian, Analyzers, Relays) | Site |  |  | 2
3 | 7 | Install account access to the server and DB | IT\OT |  |  |  | 7 | Identify devices NOT managed by Process Control (Reliability, Electrical assets) | Site |  |  | 2,7
3 | 8 | [5 empty] | 8 | Document network architecture (L1→L2→L4→L5) with IP ranges and VLANs | IT/OT |  |  | 2
3 | 9 | [5 empty] | 9 | Verify all L1 devices accessible from designated L2 workstation | Site |  |  | 8
3 | 10 | [5 empty] | 10 | Identify unsupported devices (Honeywell TDC2000, Foxboro I/A, obsolete systems) | Site |  |  | 7,8
3 | 11 | [5 empty] | 11 | Document external reference systems (Allen-Bradley, Triconex, Bently Nevada) | Site |  |  | 7,8
3 | L4 SQL server accounts and permissions | [5 empty] | 3. Program Accessibility Verification
4 | 12 | Emails enabled | IT\OT |  |  |  | 12 | Verify DCS backup files accessible (EPKS: .bak, .bkp, .stn) | Site |  |  | 4
4 | 13 | SQL jobs created | Custom |  |  |  | 13 | Verify PLC programs accessible (RSLogix .ACD/.RSS, Control Studio) | Site |  |  | 4
4 | 14 | Accounts\permissions | IT\OT |  |  |  | 14 | Verify Safety system exports available (Triconex, Safety Manager) | Site |  |  | 4
4 | 15 | MarathonCustom DB created | Custom |  |  |  | 15 | Verify Historian configuration exports (PHD, OSIPi) | Site |  |  | 4
4 | Custom Solutions readiness | [5 empty] | 16 | Document program versions and last backup dates | Site |  |  | 12-15
5 | 16 | Mitigate if not ready | Custom |  |  |  | 17 | Test restore/open programs on workstation to confirm readability | Site |  |  | 12-15
5 | 17 | Consistent Backup across all servers is critical | Custom
5 | Review and mitigate known ACM-APO gaps | [5 empty] | 4. Installation Decision (Onsite vs Remote)
6 | 18 | Custom solutions not available (yet) |  |  |  |  | 18 | Assess site network security and remote access capability | IT/OT |  |  | 3,8
6 | 19 | WARNING: Old import files not valid any more | Custom |  |  |  | 19 | Evaluate travel cost ($15K-$25K) vs security/policy constraints | Site |  |  | 3
6 | 20 | [5 empty] | 20 | If onsite: Reserve consultant workspace and schedule site access badging | Site |  |  | OSW complete
6 | 21 | [5 empty] | 21 | If remote: Validate VPN/remote desktop performance with test session | IT/OT |  |  | 3,8,23
6 | 22 | [5 empty] | 22 | Confirm Carbon Black/antivirus exceptions for Hexagon utilities | IT/OT |  |  | 23
6 | 23 | [5 empty] | 23 | Document decision in OSW with rationale | Site |  |  | All above
6 | Order of installation
7 | 24 | Do not install without cleanup and hierarchies adjustments first | Site
7 | 25 | HAMR230 first or APO+HAMR
7 | 26
7 | 27
7 | 28
7 | 29
30

## 3-OSW Completion
# | Item # | Task | Owner | Status | Notes | Prerequisites | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Onsite Scoping Workbook (OSW) Data Entry | [5 empty] | 1. Onsite Scoping Workbook (OSW) Data Entry
2 | 1 | Need to see the vendor FDS | Vendor |  |  |  | 24 | Complete Asset Hierarchy section (Site→Area→Unit→System→Subsystem) | Site |  |  | 1-6
2 | 2 |  | IT\OT |  |  |  | 25 | Validate hierarchy matches FDS (Functional Design Specification) standards | Site |  |  | 30
2 | 3 |  | Vendor |  |  |  | 26 | Complete Device Inventory with manufacturer, model, communication protocol | Site |  |  | 7-11
2 | 4 |  | Custom |  |  |  | 27 | Identify and classify external reference devices (import vs manual entry) | Site |  |  | 10,11
2 | 5 | [5 empty] | 28 | Document unsupported devices with justification for inclusion/exclusion | Site |  |  | 10
2 | External Reference Configuration | [5 empty] | 2. External Reference Configuration
3 | 6 | [5 empty] | 29 | For ControlLogix/CompactLogix: Provide .L5X/.L5K export and I/O configuration | Site |  |  | 13
3 | 7 | [5 empty] | 30 | For PLC5/SLC: Provide .RSS export and addressing scheme | Site |  |  | 13
3 | 8 | [5 empty] | 31 | For Triconex: Confirm EPKS External Reference or TPS import method | Site |  |  | 14,15
3 | 9 | [5 empty] | 32 | For Bently Nevada 3500/3600: Confirm DCS External Reference method | Site |  |  | 11
3 | 10 | [5 empty] | 33 | For Analyzers/Relays: Decide manual entry vs automated import | Site |  |  | 11
3 | 11 | [5 empty] | 34 | Document all external reference connection strings and update frequencies | Site |  |  | 35-40
3 | OSW Validation & Sign-Off | [5 empty] | 3. OSW Validation & Sign-Off
4 | 12 | [5 empty] | 35 | Hexagon reviews completed OSW for data completeness and accuracy | Hexagon |  |  | 30-35
4 | 13 | [5 empty] | 36 | Site reviews and confirms all devices in scope (NO additions after sign-off) | Site |  |  | 36
4 | 14 | [5 empty] | 37 | IT reviews network architecture and server requirements | IT/OT |  |  | 3,8
4 | 15 | [5 empty] | 38 | Executive sponsor signs off: Scope locked, no additions without Change Order | Site |  |  | 36,37
4 | 16 | Deployment timeline and resource estimate | Vendor |  |  |  | 39 | Hexagon provides deployment timeline and resource estimate | Hexagon |  |  | 38
4 | 17 | [5 empty] | 40 | Site confirms budget availability for estimated scope | Site |  |  | 39
4 | 18 | Document lessons learned: "If scope changes after sign-off, expect Change Orders" | Site |  |  |  | 41 | Document lessons learned: "If scope changes after sign-off, expect Change Orders" | Site |  |  | 38,39
Site
IT\OT
Vendor
Custom

## 4-Deployment Readiness
# | Item # | Task | Owner | Status | Notes | Prerequisites | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Backups | [5 empty] | 1. DCS Data Collection (Honeywell EPKS/TPS)
2 | 1 | Release all consoles | Site |  |  |  | 72 | Import baseline DCS hierarchy (Stations, Entities, Displays, Control Modules) | Hexagon |  |  | 42,51
2 | 2 | Backup DBs and Files | Site |  |  |  | 73 | Import alarm configuration (Priority, Deadband, Shelving) | Hexagon |  |  | 59
2 | 3 | [5 empty] | 74 | Import I/O configuration (FTA/MTA channels, wiring terminations) | Hexagon |  |  | 59
2 | General | [5 empty] | 75 | Import control strategies (CM logic, function blocks) | Hexagon |  |  | 59
3 | 4 | ACM Test Server operational | Site |  |  |  | 76 | Import HMI displays (navigation, faceplate associations) | Hexagon |  |  | 59
3 | 5 | Hierarchies optimal - EMDB \ ACM | IT\OT |  |  |  | 77 | Validate imported data matches live system (spot-check 10% of tags) | Site |  |  | 59-63
| 6 | Hierarchies optimal - M&R | Vendor
| 7 | ACM DB cleanup complete | Custom
| 8 | M&R cleanup complete
| 9 | Folders with scripts (e.g. Backup) copied to new servers
10
11
| 12 | ACM Health Checks. Repeat checks (same health check scripts) from cleanup section.
13
14
3 | 15 | [5 empty] | 78 | Document import statistics: Total tags, CM blocks, displays, alarms | Hexagon |  |  | 63
16
3 | ACM DB preparation | [5 empty] | 2. PLC Data Collection (Allen-Bradley, Modicon)
4 | 16 | ACM DB prevent accidental Enforce | Site |  |  |  | 79 | Import PLC programs (ladder logic, structured text) | Hexagon |  |  | 52
4 | 17 | ACM DB prevent OPC overload | Site |  |  |  | 80 | Extract I/O configuration (local/remote racks, addressing) | Hexagon |  |  | 64
4 | 18 | Disable Enforcements | Site |  |  |  | 81 | Map PLC tags to DCS external references (if applicable) | Site |  |  | 35,64
4 | 19 | Re-run and Disable TagSyncs | Site |  |  |  | 82 | Import PLC documentation (tag descriptions, rung comments) | Hexagon |  |  | 64
4 | 20 | Change enforcer name in DB (not in UI as it will remove from production) | Site
4 | 21 | Delete all Deleted Tags | Site |  |  |  | 83 | Validate imported data: Check tag counts, rung accuracy | Site |  |  | 64,65
4 | 22 | Export all consoles and all versions | Site
4 | 23 | Ensure only 2 versions of variables | Site
4 | 24 | Export all consoles and all versions | Site
4 | 25 | Delete BMA points… if < APO3.1 | Site
4 | M&R DB preparation | [5 empty] | 3. Safety System Data Collection (Triconex, Safety Manager)
5 | 26 | none if cleanup done (just re-run Health Check scripts) |  |  |  |  | 84 | Import Safety system configuration (logic, I/O) | Hexagon |  |  | 53
5 | 27 | [5 empty] | 85 | Import Safety interlock matrix (cause-effect) | Hexagon |  |  | 66
5 | 28 | [5 empty] | 86 | Map Safety system tags to DCS (if EPKS External Reference) | Site |  |  | 36,66
5 | 29 | [5 empty] | 87 | Validate critical safety logic accuracy (SIS-rated tags) | Site |  |  | 66,67
5 | 30 | [5 empty] | 88 | Document Safety system version and last MOC date | Hexagon |  |  | 67
5 | APO Install selections \ standards | [5 empty] | 4. Reliability & Electrical Systems
6 | 31 | Folders location |  |  |  |  | 89 | Import Bently Nevada vibration monitoring configuration | Hexagon |  |  | 37
6 | 32 | Schema name |  |  |  |  | 90 | Import relay/protection device configuration (SEL, GE, ABB) | Site |  |  | 11
6 | 33 | Service name |  |  |  |  | 91 | Import motor control center (MCC) lineup data | Site |  |  | 11
6 | 34 | [5 empty] | 92 | Import electrical single-line diagram references | Site |  |  | 11
6 | 35 | [5 empty] | 93 | Validate reliability data matches CMMS (SAP PM) asset register | Site |  |  | 68,69
6 | Configuration standarts | [5 empty] | 5. Historian Data Collection (OSIPi, PHD)
7 | 36 | Site name LARC, LARW, ANR etc |  |  |  |  | 94 | Import Historian tag list (process variables) | Hexagon |  |  | 54
7 | 37 | RDM - do not use 1, recommended e.g. OPC3, OPC4 |  |  |  |  | 95 | Map Historian tags to DCS/PLC source tags | Hexagon |  |  | 70
7 | 38 | [5 empty] | 96 | Import Historian AF (Asset Framework) hierarchy if applicable | Hexagon |  |  | 70
7 | 39 | [5 empty] | 97 | Validate Historian data completeness (check critical KPIs exist) | Site |  |  | 70,71
7 | Migration standards | [5 empty] | 6. Data Quality Checks
8 | 40 | Hierarchy choice during DB migration |  |  |  |  | 98 | Verify no duplicate assets (same tag in multiple systems) | Hexagon |  |  | 72
8 | 41 | [5 empty] | 99 | Verify asset hierarchy compliance (Area/Unit/System matches FDS) | Site |  |  | 30,72
8 | 42 | [5 empty] | 100 | Verify external reference connections functional (live data updates) | Site |  |  | 40,73
8 | 43 | [5 empty] | 101 | Verify I/O addressing consistency (no conflicts) | Hexagon |  |  | 72
8 | 44 | [5 empty] | 102 | Resolve data quality issues before proceeding to validation phase | Site |  |  | 72,73
8 | 45 | [5 empty] | 103 | Document data collection completion metrics (total assets, tags, connections) | Hexagon |  |  | 73
8 | 46 | [5 empty] | 104 | Archive all import source files (backups, exports) for future reference | Site |  |  | 73
Site
IT\OT
Vendor
Custom

## 5-Validation & Go-Live
# | Item # | Task | Owner | Status | Notes | Prerequisites (scripts) | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Site Acceptance Testing (SAT) | [5 empty] | 1. Site Acceptance Testing (SAT)
2 | 1 |  | Site |  |  |  | 105 | Verify asset search functionality (find by tag, description, hierarchy) | Site |  |  | 73
2 | 2 |  | IT\OT |  |  |  | 106 | Verify signal tracing (follow tag from PLC→DCS→Historian) | Site |  |  | 74
2 | 3 |  | Vendor |  |  |  | 107 | Verify external reference data updates (live PLC tag values) | Site |  |  | 40,74
2 | 4 |  | Custom |  |  |  | 108 | Verify alarm configuration accuracy (priority, setpoints) | Site |  |  | 63,75
2 | 5 | [5 empty] | 109 | Verify reports generation (asset inventory, change history) | Site |  |  | 75
2 | 6 | [5 empty] | 110 | Verify user permissions (read-only vs admin access) | Site |  |  | 49,76
2 | 7 | [5 empty] | 111 | Document SAT results: Pass/Fail with defect list | Site |  |  | 76
2 | User Training | [5 empty] | 2. User Training
3 | 8 | Refresher M&R |  |  |  |  | 112 | Train Process Engineers: Asset search, signal tracing, alarm review | Hexagon |  |  | 76
3 | 9 | Refresher ACM-APO "same functionality" + what was lost |  |  |  |  | 113 | Train Reliability Engineers: Equipment hierarchy, vibration monitoring integration | Hexagon |  |  | 76
3 | 10 | Basic new workflow |  |  |  |  | 114 | Train Electrical Engineers: Relay/protection device configuration, single-line diagrams | Hexagon |  |  | 76
3 | 11 | Advanced (rationalization expert for consulting on optimal settings) |  |  |  |  | 115 | Train IT/Administrators: User management, backup/restore, troubleshooting | Hexagon |  |  | 76
3 | 12 | [5 empty] | 116 | Provide training materials: User guides, quick reference cards, video tutorials | Hexagon |  |  | 77
3 | 13 | [5 empty] | 117 | Schedule refresher training session (4-6 weeks post go-live) | Site |  |  | 77
3 | Go-Live Preparation | [5 empty] | 3. Go-Live Preparation
4 | 14 | Freeze |  |  |  |  | 118 | Finalize production database with all SAT defects resolved | Hexagon |  |  | 76,78
| 15 | Health check scripts
4 | 16 | Experion Servers: Alarm Help |  |  |  |  | 119 | Configure automated data refresh schedule (nightly imports) | Hexagon |  |  | 78
4 | 17 | Dynamic mode management |  |  |  |  | 120 | Configure automated SQL backup schedule (daily full + hourly log) | IT/OT |  |  | 44,79
4 | 18 | Custom solutions |  |  |  |  | 121 | Publish L5 web URL to enterprise users | IT/OT |  |  | 79
4 | 19 | Switch TagSync \ check Windows tasks |  |  |  |  | 122 | Create Integrity support contact list (Hexagon PM, Site Lead, IT support) | Site |  |  | 79
4 | 20 | Disable enforcements \ check Windows tasks |  |  |  |  | 123 | Announce go-live date and user access instructions (email, intranet) | Site |  |  | 80
4 | 21 | No Enforcements or TagSyncs overlapping |  |  |  |  | 124 | Execute final pre-production backup | IT/OT |  |  | 79
4 | Post-Go-Live Support | [5 empty] | 4. Post-Go-Live Support
5 | 22 | [5 empty] | 125 | Monitor data import jobs for failures (first 2 weeks critical) | Hexagon |  |  | 80
5 | 23 | [5 empty] | 126 | Address user-reported issues within 48 hours | Site |  |  | 80
5 | 24 | [5 empty] | 127 | Track usage metrics (logins, searches, reports) | IT/OT |  |  | 81
5 | 25 | [5 empty] | 128 | Schedule 2-week post-go-live checkpoint meeting | Site |  |  | 81
5 | 26 | [5 empty] | 129 | Schedule 1-month post-go-live review (lessons learned) | Site |  |  | 81
5 | 27 | [5 empty] | 130 | Transition support from Hexagon to Site/IT (knowledge transfer) | Site |  |  | 81
5 | 28 | [5 empty] | 131 | Archive project documentation (OSW, imports, SAT, training materials) | Site |  |  | 81
5 | 29 | [5 empty] | 132 | Update site runbook with Integrity troubleshooting procedures | IT/OT |  |  | 81
5 | 30 | [5 empty] | 133 | Close project and release Hexagon resources | Site |  |  | All above
5 | Testing (scripts)
6 | 31 | Add Tag and Propose \ Release
6 | 32 | Enforcements
6 | 33 | M&R integration test
6 | 34 | Tags Count |  |  |  | ACM Count Tags and its versions.sql
6 | 35 | Enforcements and errors |  |  |  | ACM Get Enforcement Log.sql
6 | 36 | Alarm Help - Alarm Summary
6 | 37 | Alarm Help - Web view
6 | 38
6 | 39
6 | Capture all suggestions \ concerns
7 | 40
7 | 41 | Should
7 | 42
7 | 43
7 | 44
7 | 45
7 | 46
7 | 47
7 | 48
Site
IT\OT
Vendor
Custom

## 6-Parallel run
# | Item # | Task | Owner | Status | Notes | Prerequisites
1 | What to compare
2 | 1 |  | Site
2 | 2 |  | IT\OT
2 | 3 |  | Vendor
2 | 4 |  | Custom
2 | 5
2 | 6
2 | 7
2 | What to test
3 | 8
3 | 9
3 | 10
3 | 11
3 | 12
3 | 13
3 | 14
3 | HowTo temporary switch, then undo (if needed)
4 | 15
4 | 16
4 | 17
4 | 18
4 | 19
4 | 20
4 | 21
4 | Notifications??
5 | 22
5 | 23
5 | 24
5 | 25
5 | 26
5 | 27
5 | 28
5 | 29
5 | 30
Site
IT\OT
Vendor
Custom

## 7-Decomission
# | Item # | Task | Owner | Status | Notes | Prerequisites | Item # | Task | Owner | Status | Notes | Prerequisites
1 | Freeze and Delta import | [5 empty] | 1. DCS Data Collection (Honeywell EPKS/TPS)
2 | 1 | ACM using change history log | Site |  |  |  | 72 | Import baseline DCS hierarchy (Stations, Entities, Displays, Control Modules) | Hexagon |  |  | 42,51
2 | 2 | ACM other logs |  |  |  |  | 73 | Import alarm configuration (Priority, Deadband, Shelving) | Hexagon |  |  | 59
2 | Switch | [5 empty] | 74 | Import I/O configuration (FTA/MTA channels, wiring terminations) | Hexagon |  |  | 59
3 | 3 | Freeze | Site |  |  |  | 75 | Import control strategies (CM logic, function blocks) | Hexagon |  |  | 59
3 | 4 | Experion Servers: Alarm Help | IT\OT |  |  |  | 76 | Import HMI displays (navigation, faceplate associations) | Hexagon |  |  | 59
3 | 5 | Dynamic mode management | Vendor |  |  |  | 77 | Validate imported data matches live system (spot-check 10% of tags) | Site |  |  | 59-63
3 | 6 | Custom solutions | Custom |  |  |  | 78 | Document import statistics: Total tags, CM blocks, displays, alarms | Hexagon |  |  | 63
3 | 7 | Switch TagSync \ check Windows tasks |  |  |  |  | 2. PLC Data Collection (Allen-Bradley, Modicon)
3 | 8 | Disable enforcements \ check Windows tasks |  |  |  |  | 79 | Import PLC programs (ladder logic, structured text) | Hexagon |  |  | 52
3 | 9 | No Enforcements or TagSyncs overlapping |  |  |  |  | 80 | Extract I/O configuration (local/remote racks, addressing) | Hexagon |  |  | 64
3 | KEEP ACM SERVER (JUST IN CASE) | [5 empty] | FOR | Map PLC tags to DCS external references (if applicable) | Site |  |  | 35,64
4 | 10 | Power off but… keep the server |  |  |  |  | 82 | Import PLC documentation (tag descriptions, rung comments) | Hexagon |  |  | 64
4 | 11
4 | 12 | [5 empty] | 83 | Validate imported data: Check tag counts, rung accuracy | Site |  |  | 64,65
4 | 13
4 | 14
4 | 15
4 | 16
4 | 17 | [5 empty] | 3. Safety System Data Collection (Triconex, Safety Manager)
4 | 18 | [5 empty] | 84 | Import Safety system configuration (logic, I/O) | Hexagon |  |  | 53
4 | 19 | [5 empty] | 85 | Import Safety interlock matrix (cause-effect) | Hexagon |  |  | 66
3 | Cleanup | [5 empty] | 86 | Map Safety system tags to DCS (if EPKS External Reference) | Site |  |  | 36,66
4 | 10 | Host files update |  |  |  |  | 87 | Validate critical safety logic accuracy (SIS-rated tags) | Site |  |  | 66,67
4 | 11 | un-DSA EAS\ACM server |  |  |  |  | 88 | Document Safety system version and last MOC date | Hexagon |  |  | 67
4 | 12 | Uninstall Remaining ACM clients |  |  |  |  | 4. Reliability & Electrical Systems
4 | 13 | Disable L4 ACM Web |  |  |  |  | 89 | Import Bently Nevada vibration monitoring configuration | Hexagon |  |  | 37
4 | 14 | Disable replication (if not needed) |  |  |  |  | 90 | Import relay/protection device configuration (SEL, GE, ABB) | Site |  |  | 11
4 | 15 | [5 empty] | 91 | Import motor control center (MCC) lineup data | Site |  |  | 11
4 | 16 | [5 empty] | 92 | Import electrical single-line diagram references | Site |  |  | 11
4 | 17 | [5 empty] | 93 | Validate reliability data matches CMMS (SAP PM) asset register | Site |  |  | 68,69
4 | 18 | [5 empty] | 5. Historian Data Collection (OSIPi, PHD)
4 | 19 | [5 empty] | 94 | Import Historian tag list (process variables) | Hexagon |  |  | 54
4 | Cleanup M&R | [5 empty] | 95 | Map Historian tags to DCS/PLC source tags | Hexagon |  |  | 70
5 | 20 | [5 empty] | 96 | Import Historian AF (Asset Framework) hierarchy if applicable | Hexagon |  |  | 70
5 | 21 | [5 empty] | 97 | Validate Historian data completeness (check critical KPIs exist) | Site |  |  | 70,71
5 | 22 | [5 empty] | 6. Data Quality Checks
5 | 23 | [5 empty] | 98 | Verify no duplicate assets (same tag in multiple systems) | Hexagon |  |  | 72
5 | 24 | [5 empty] | 99 | Verify asset hierarchy compliance (Area/Unit/System matches FDS) | Site |  |  | 30,72
[7 empty] | 100 | Verify external reference connections functional (live data updates) | Site |  |  | 40,73
[7 empty] | 101 | Verify I/O addressing consistency (no conflicts) | Hexagon |  |  | 72
[7 empty] | 102 | Resolve data quality issues before proceeding to validation phase | Site |  |  | 72,73
[7 empty] | 103 | Document data collection completion metrics (total assets, tags, connections) | Hexagon |  |  | 73
[7 empty] | 104 | Archive all import source files (backups, exports) for future reference | Site |  |  | 73
Site
IT\OT
Vendor
Custom