## Applications Dashboard
APPLICATIONS DASHBOARD — 2025-Q4
Total Application Issues: | 31
Estimated Hours Invested: | 52
Issues by Application:
Alarm Management (DynAMo/ACM/APO): | 18 (58%)
Asset Integrity: | 7 (23%)
Other Applications: | 5 (16%)
Historian (PHD/PI): | 1 (3%)
Business Impact:
Compliance: | 15
Low: | 14
Efficiency: | 2
Application Issues:
Date | System | Summary | Complexity | Resolution | Impact
2025-10-07 | Historian | RE: Marathon ¦ St Paul ¦ Pre-Onsite Visit: Clarified PI vs. | Low | Informational | Low
2025-10-27 | Alarm | Deployed patched SyncDriver DLL for Dynamo fix | Low | Fixed | Low
2025-10-28 | Alarm | Workaround for ACM PT DESC update via Station F12 | Low | Workaround | Low
2025-10-29 | Alarm | Clarified alarm governance L4/L3 for APO/ACM | Low | Informational | Low
2025-10-30 | Integrity | Created scheduled task to move EPKS files on LARINT01 | Low | Pending | Compliance
2025-12-03 | Alarm: ACM | Flagged ACM tag description mismatches, noted F12 forcing up | Low | Informational | Low
2025-12-04 | APO/HAM | Node rename procedure missing; SR needed | Quick | Escalated | Low
2025-12-04 | HMI: HMIWeb | Explained Flex vs server alarm discrepancies under investiga | Low | Pending | Low
2025-12-05 | Integrity | Requested SEL‑710 relay config files for Integrity ingestion | Low | Pending | Compliance
2025-12-10 | Alarm: ACM | Enabled ETD Tag Sync, issued Add/Delete lists, noted need fo | Moderate | Pending | Compliance
2025-12-10 | Alarm: ACM | Explained SCADA Reconfiguration defect causing Alarm Help lo | Low | Escalated | Low
2025-12-11 | Alarm Mgmt | RE: APO 3.0 Installation: Raised L3/L4 edit constraints and | Low | Informational | Compliance
2025-12-11 | Alarm Mgmt | RE: Console / Dynamo: Explained suppression exposure vs. NTE | Low | Informational | Compliance
2025-12-11 | Alarm Mgmt | RE: ETD_UTIL: Provided Tag Sync add/delete lists and reasoni | Low | Fixed | Compliance
2025-12-11 | Experion/TPS | RE: Significant issue with alarm discrepancies occurring bet | Medium | Informational | Compliance
2025-12-11 | Alarm: DynAMo | Clarified INHIBIT vs DISABLE behavior and recommended proper | Quick | Workaround | Compliance
2025-12-11 | Alarm: APO | Recommended APO 3.0 template strategy and cautioned on alter | Medium | Informational | Efficiency
2025-12-11 | Alarm: ACM | Diagnosed unexplained In Progress state for tag 88VA327G lin | Low | Pending | Low
2025-12-14 | ACM/SCADA | DB corruption and SR tracking | Major | Escalated | Low
2025-12-16 | Alarm Mgmt | SPW Dynamo Activities: Investigated bulk UnSuppress actions | Low | Fixed | Compliance
2025-12-17 | Experion/TPS | RE: LCN3 (ALKY) DCS Backup and Integrity Update: Coordinated | Low | Fixed | Compliance
2025-12-18 | Integrity | Challenged reservation migration hours, documented SSR defec | Moderate | Escalated | Compliance
2025-12-19 | Experion/TPS | RE: LCN4 17XA861 and 84UA822 chattering alarms: Clarified IN | Medium | Informational | Low
2025-12-19 | Alarm: DynAMo | Supported mitigation of LCN4 chattering alarms with suppress | Quick | Workaround | Low
2025-12-29 | SIS/Triconex | RE: Integrity TS1131 cannot view XPS: Pursued PDF-based work | High | Workaround | Compliance
2025-12-29 | Alarm Mgmt | RE: ACM Secondary Parameter Update: Ran secondary parameter | Low | Fixed | Efficiency
2025-12-29 | Alarm Mgmt | RE: ALERT: ACM DB Replication Heartbeat not implemented or c | High | Fixed | Compliance
2025-12-29 | Integrity (ALI) | RE: Zip files transferred correctly as well: Verified transf | Low | Fixed | Compliance
2025-12-31 | Experion/TPS | RE: DAS 91DAS005: Chased missing SUPP events on DAS triggers | Low | Fixed | Low
2025-12-31 | Integrity | Completed manual migration of >1000 reservations to LARINT01 | High | Fixed | Compliance
2025-12-31 | Alarm: DynAMo | Troubleshot missing DAS SUPP events since Oct 4 and document | Moderate | Workaround | Low
RECOMMENDATION: Recognize application support as a distinct skill set requiring dedicated expertise.